## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 0
Deployment | 80
Overall
Team Size
Name | Role | Count
Fe | SSE | 1
Fe | SE | 0
Be | SSE | 1
Be | SE | 0
Ux | UIUX_DESIGNER | 2
Team Hours
Team | Hr / Day
ba | 2
lead | 0
qa | 2
uiux_ba | 2
uiux_lead | 2
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
Customer App | Customer App - Summary
Employee App | Employee App - Summary
Admin Panel | Admin Panel - Summary
Integration | Integration - Summary
Sub Total

## Customer App - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Sign up + Login | Mobile Number + OTP | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 3
Sign up + Login | Login via Email + Password | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Sign up + Login | Registration Form (May be) | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
Sign up + Login | Login via Google | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Sign up + Login | Login via Apple | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Sign up + Login | Forgot Password | Email verification | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Sign up + Login | Forgot Password | Change Password | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Quick Dashboard | Total bookings made | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 8 | 5 | 8
Quick Dashboard | Total money spent | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 0 | 0 | 0
Quick Dashboard | Savings from discounts | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
Quick Dashboard | Upcoming Bookings | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
My Units (Vehicles) | Vehicles List | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 5 | 3 | 5
My Units (Vehicles) | View Vehicle Details | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 3 | 3
My Units (Vehicles) | Hero banner / Ads | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 3 | 2 | 2
My Units (Vehicles) | Transfer Ownership to other member / Request transfer of ownership | Basic Form | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 2 | 3
My Units (Vehicles) | Transfer Ownership to other member / Request transfer of ownership | Upload Documents | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 5
My Units (Vehicles) | Request transfer of ownership | Basic Form | [7 empty] | Simple | Must Have
My Units (Vehicles) | Request transfer of ownership | Upload Documents | [7 empty] | Simple | Must Have
My Units (Vehicles) | Ownership Requests | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
My Units (Vehicles) | Ownership Requests | Accept or Reject request | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Units (Vehicles) | Ownership Requests | Add Additional Notes | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 3
Book a Service | Search, Sort and Filter | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Book a Service | List | List View | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Book a Service | List | Grid view | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Book a Service | Service Details page | Service Banner | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Book a Service | Service Details page | Service Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Book a Service | Service Details page | Service Pricing | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Book a Service | Service Details page | View Ratings and Reviews | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Customer) | Select the Registered Vehicle | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Customer) | Customer select their Location | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Book a Service | Book a Service (Customer) | Nearby Stores must be displayed | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 5
Book a Service | Book a Service (Customer) | Customer adds notes | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
Book a Service | Book a Service (Customer) | Date and Time Slot selection for Drop off | [7 empty] | Simple | Must Have | [5 empty] | 0 | 2 | 1 | 2
Book a Service | Book a Service (Customer) | Upload Images (Optional) | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
Book a Service | Book a Service (Customer) | Booking confirmation | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select the registered Vehicle | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select - Basic Service or Breakdown | Decided to include towing vehicle or not | [6 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select preferred date + Time to pickup | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select the unit (Garage) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select - Regular or Emergency | Can be used for road side assistance | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select - Self pick up, Need assistance in Drop off | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Based on the info, time slots will be displayed for selection | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select time slots | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Booking confirmation | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Tracking info of rider will be generated on Whatsapp when the job is in progress |  |  | Assuming the service vehicle has IoT device installed in it and the tracking information will be provided by the same |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Towing of vehicle - if respective pickup option is selected | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Select Location / Address |  |  | Google Places API |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 3
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Provide additional Landmark comments | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Additional text box for the problem description | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Call / Chat with us - icon | This will navigate to WhatsApp for chat and dialer app for calls | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 1
Book a Service | Book a Service (Off-site - Includes pick up and Drop off) | Upload Images (Optional) | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
My Bookings | Booking List | Search, Sort and Filter | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
My Bookings | Booking List | Upcoming List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
My Bookings | Booking List | Completed List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
My Bookings | Booking List | Cancelled List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
My Bookings | Booking List | Paused List | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Bookings | View Booking Details | Date and Time of Service | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
My Bookings | View Booking Details | Service Details + Service Provider info | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
My Bookings | View Booking Details | Images uploaded during service | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 2
My Bookings | View Booking Details | Reports - View + Download | Images attached during service, invoice details will be included | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 5 | 5
My Bookings | View Booking Details | Estimations - Approve or Request for Revision | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 5 | 3
My Bookings | View Booking Details | View Invoice | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 2
My Bookings | View Booking Details | Download Invoice | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 0
My Bookings | View Booking Details | Make a Payment |  |  | Payment flow integration |  |  |  |  | Simple | Must Have | [6 empty] | 21 | 8 | 21
My Bookings | Action :: Cancel booking (Upcoming) | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
My Bookings | Action :: Provide Reviews for Completed Bookings | Provide Star Rating | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 0
My Bookings | Action :: Provide Reviews for Completed Bookings | Provide Description | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
My Bookings | Action :: Provide Reviews for Completed Bookings | Submit | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
My Bookings | Track the Service Provider location | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Bookings | Credit Balance Overview | Outstanding Balance for Specific Booking | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 3 | 1 | 2
My Bookings | Credit Balance Overview | Due Date | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
My Bookings | Credit Balance Overview | Pay Now button |  |  | Payment gateway integrated on the button |  |  |  |  | Simple | Must Have | [5 empty] | 2 | 2 | 1 | 3
My Bookings | Credit Balance Overview | Overall Dashboard in Bookings Page - showing statistics of amount spent, amount outstanding, amount paid | [7 empty] | Simple | Must Have |  |  |  |  | 5 | 5 | 8 | 5 | 5
In App Messaging | Chat with Service Provider for the Upcoming Task | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 13 | 5 | 2
In App Messaging | Conversation Threads (History) | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 3 | 3
In App Messaging | Conversation Screen | Add Text | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 1 | 1 | 0
In App Messaging | Conversation Screen | Add Attachment | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
In App Messaging | Send | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
Notifications (App + Push Notifications) | Appointment updates | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 5 | 13
Notifications (App + Push Notifications) | New Messages | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
Notifications (App + Push Notifications) | Job Status Updates | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
Notifications (App + Push Notifications) | Payment Due | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Notifications (App + Push Notifications) | Payment Received | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Notifications (App + Push Notifications) | Pending Approval for Estimation | Accept or Reject | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Whatsapp Booking Integration | Business API setup | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 89
Whatsapp Booking Integration | Welcome Message | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 2
Whatsapp Booking Integration | Booking Initiation | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 5
Whatsapp Booking Integration | Service Options | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 8
Whatsapp Booking Integration | Date and Time Collection | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 5
Whatsapp Booking Integration | Availability Confirmation | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 3
Whatsapp Booking Integration | Booking Confirmation | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 2
Whatsapp Booking Integration | Reminder Message | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 5
Whatsapp Booking Integration | Feedback Request | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 34
Whatsapp Booking Integration | Service Promotion | [8 empty] | Simple | Must Have
Whatsapp Booking Integration | Handling FAQs | [8 empty] | Simple | Must Have
Whatsapp Booking Integration | Unavailable Time Slots | [8 empty] | Simple | Must Have
Whatsapp Booking Integration | Follow-Up for Cancellations | [8 empty] | Simple | Must Have
Email + WhatsApp Notification (Integration) | Appointment Reminders | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 3
Email + WhatsApp Notification (Integration) | Job Status | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Email + WhatsApp Notification (Integration) | Payment Receipts | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 8
Profile | View / Edit Profile Details | Name, Email, Phone Number | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Profile | View / Edit Profile Details | View Password | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Profile | View / Edit Profile Details | Change Password | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Profile | My Ratings | Ratings List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Profile | My Ratings | Search, Sort and Filter | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Profile | My Ratings | View Review details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 1 | 2
Profile | My Ratings | Google Intergration | [7 empty] | Simple | Must Have
Profile | Customer Support via Whatsapp |  |  |  | Launch WhatsApp directly |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 1
Profile | Language | Arabic | [7 empty] | Simple | Must Have | [5 empty] | 8 | 5 | 1 | 1
Profile | Language | English | [7 empty] | Simple | Must Have | [5 empty] | 0 | 5 | 1 | 1
Profile | Logout | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
UX Process | Requirement Gathering | [8 empty] | Simple | Must Have |  |  |  |  | 8
UX Process | Brainstorming & Research | [8 empty] | Simple | Must Have |  |  |  |  | 13
UX Process | User Flow | [8 empty] | Simple | Must Have |  |  |  |  | 13
UX Process | Competitive Analysis | [8 empty] | Simple | Must Have |  |  |  |  | 13
Style Guide | [9 empty] | Simple | Must Have | [5 empty] | 8
Prototype | [9 empty] | Simple | Must Have | [5 empty] | 13
Splash Screen - For Mobile | [9 empty] | Simple | Must Have | [5 empty] | 8 | 2 | 1 | 0
Tab Responsive | [9 empty] | Simple | Must Have | [5 empty] | 55 | 34 | 0 | 0
Mobile Responsive | [9 empty] | Simple | Must Have | [5 empty] | 34 | 34 | 0 | 0

## Admin Panel - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login | Via Email and Password | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 2 | 3
Login | Forgot Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 3
Dashboard | Visualisation | Total Jobs | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 3 | 5
Dashboard | Visualisation | Total Revenue | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 3 | 3 | 5
Dashboard | Visualisation | Total Customers | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 3 | 3 | 5
Dashboard | Visualisation | Job Status Real time updates | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Dashboard | Visualisation | Assigned ¦ Unassigned Jobs | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Dashboard | Respective Filters | Weekly | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 8 | 5 | 8
Dashboard | Respective Filters | Monthly | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Dashboard | Respective Filters | Yearly | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
User Management | User List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 2 | 2
User Management | User List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
User Management | User List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 3 | 3
User Management | User List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
User Management | Add User | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
User Management | View User Details | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
User Management | Edit User Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 3 | 3
User Management | Enable/Disable User | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 2
User Management | Delete User | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 2
Role Management | Role List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 2 | 2
Role Management | Role List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Role Management | Role List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 3 | 3
Role Management | Role List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Role Management | View Role Details | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Role Management | Add Role |  |  |  | Modules list API is considered as part of this. so Dynamically role can be created with respective permissions. |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
Role Management | Edit Role Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 3 | 3
Role Management | Enable/Disable Role | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 2
Role Management | Delete Role | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 2
Appointment Management | Appointment List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 2 | 2
Appointment Management | Appointment List | List - Unassigned ¦ To Do ¦ In-Progress ¦ Completed ¦ Cancelled | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
Appointment Management | Appointment List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 3 | 3
Appointment Management | Appointment List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Appointment Management | View Appointment Details | Start + End - Date and Time | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 3 | 3
Appointment Management | View Appointment Details | Service Details | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Appointment Management | View Appointment Details | Current Status of Appointment | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 2 | 2
Appointment Management | Actions on Appointment | Approve - Set Assignee + Add Equipments Details + Additional note | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Appointment Management | Actions on Appointment | Reject | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Appointment Management | Actions on Appointment | Reschedule | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 3
Appointment Management | Actions on Appointment | Unassign task | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Appointment Management | Selection of Assignee | Employees List who are available on that specific day | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Appointment Management | Selection of Assignee | Also allow to search for Specific employee | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Appointment Management | Selection of Assignee | Assign Task | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Appointment Management | Export as CSV file | [8 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 5
Customer Management | Customer List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Customer Management | Customer List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
Customer Management | Customer List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 3 | 3
Customer Management | Customer List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Customer Management | View Customer Details | View Customer Orders and Transactions | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Customer Management | View Customer Details | Customer Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 2
Customer Management | View Customer Details | View Customer Analytics | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 3
Customer Management | View Customer Details | Download Complete Customer Report | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
Customer Management | View Customer Details | Set Credit Limit | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Customer Management | View Customer Details | Upgrade their Account - Personal / Business | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Customer Management | Edit Customer Details (Contact Information) | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Customer Management | Download Customer List |  |  |  | Considered as a PDF in tabular format |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 3 | 5
Customer Management | Enable/Disable Customer | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 1
Customer Management | Credit Balance Overview | Outstanding Balance for Specific Booking | [7 empty] | Simple | Must Have |  |  |  |  | 2 |  | 2 | 1 | 1
Customer Management | Credit Balance Overview | Due Date | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
Customer Management | Credit Balance Overview | Overall Dashboard in Bookings Page - showing statistics of amount spent, amount outstanding, amount paid | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 2 | 3
Customer Management | Credit Balance Overview | Send Reminder | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
Employee Management | View Employee Details | View Employee related Analytics (In Description) | Total Number of tasks fulfilled, Total Revenue, Average Ratings and Review, To do, In Progress, Completed, Cancelled Jobs by Employee etc. | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 5
Employee Management | View Employee Details | View Basic Employee Details | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Employee Management | View Employee Details | Service Logs with Respective Status | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 2
Employee Management | View Employee Details | View Service Details | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Employee Management | View Employee Details | View Equipments / Tools Assigned | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Employee Management | View Employee Details | Assign tools or Equipment to Employee (New Form) | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Employee Management | View Employee Details | Unassign the Existing tool | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Employee Management | View Employee Details | Records of their Login | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Employee Management | Employee List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Employee Management | Employee List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 3 | 3
Employee Management | Employee List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Employee Management | Employee List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Employee Management | Edit Employee Details (Contact Information and other details) | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Employee Management | Download Employee List |  |  |  | PDF with simple table is considered |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 2 | 3
Employee Management | Enable/Disable Employee | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 1
Employee Management | Job Scheduling | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Employee Management | Assign Shift (Select from Exiting Shift) | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Transactions Management | Transaction List | List | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 2
Transactions Management | Transaction List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 1 | 2
Transactions Management | Transaction List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Transactions Management | Transaction List | Filter | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Transactions Management | View Transaction Details | View Service Details | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Transactions Management | View Transaction Details | View Invoice | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Transactions Management | View Transaction Details | Download Invoice |  |  | Format considered - PDF |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 1 | 2
Transactions Management | Export List | [8 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Backend Reminders + Email Notifications |  |  |  |  | Multiple Email Templates in Send Grid |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 21
Content Management (Additional) | Manage T&Cs | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 3
Content Management (Additional) | Manage FAQs | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Content Management (Additional) | Manage Legals | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 3 | 3 | 3
Content Management (Additional) | Manage Help center | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 3 | 3
Content Management (Additional) | Manage Privacy Policy | [9 empty] | Must Have | [6 empty] | 5 | 5 | 3
Profile | View Profile | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Profile | Edit Profile | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Profile | Change Password | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
In App Messaging | Chat with Employee / Customer related to task | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 21 | 13 | 21
In App Messaging | Conversation Threads (History) | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 13 | 8 | 8
In App Messaging | Conversation Screen | Add Text | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
In App Messaging | Conversation Screen | Add Attachment | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
In App Messaging | Send | [8 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Logout | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 2 | 0
Inventory Management | List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Inventory Management | List | Search | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Inventory Management | List | Sort | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Inventory Management | List | Filter | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Inventory Management | Grid view of Equipments | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 3 | 3
Inventory Management | View Equipment Details | General Equipment Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Inventory Management | View Equipment Details | Assigned Employee List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
Inventory Management | View Equipment Details | Un-assign the Equipments from Employee | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 2 | 1 | 1
Whatsapp Integration | Customer Support | [8 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 8
Whatsapp Integration | Progress Tracking Updates | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Unit and Documents Management (Unit Details / Asset Details) | Search, Sort, Filter | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Unit and Documents Management (Unit Details / Asset Details) | List view | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Unit and Documents Management (Unit Details / Asset Details) | Manage Units (Garages) | Create Unit - Banner, description, Maps | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 8 | 5 | 5
Unit and Documents Management (Unit Details / Asset Details) | Manage Units (Garages) | Edit Unit Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 3 | 3
Unit and Documents Management (Unit Details / Asset Details) | Manage Units (Garages) | View Unit details | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Unit and Documents Management (Unit Details / Asset Details) | Manage Units (Garages) | Delete Unit | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Manage Units (Garages) | Enable / Disable Unit | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Create Folder or Upload Folder within Unit | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Unit and Documents Management (Unit Details / Asset Details) | Folders | List View | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 2 | 1 | 2
Unit and Documents Management (Unit Details / Asset Details) | Folders | Grid View | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Unit and Documents Management (Unit Details / Asset Details) | Folders | View folder | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Folders | Edit folder Name | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Folders | Delete Folder | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Upload Documents in Folder | Upload Feature |  |  | AWS S3 |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 5 | 8
Unit and Documents Management (Unit Details / Asset Details) | Upload Documents in Folder | List view | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Upload Documents in Folder | Grid View | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Unit and Documents Management (Unit Details / Asset Details) | Upload Documents in Folder | View Documents | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Unit and Documents Management (Unit Details / Asset Details) | Upload Documents in Folder | Manage Access - Specific Department / Specific Employees / Specific Email IDs | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 5
Ratings and Review | List | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Ratings and Review | List | Search | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Ratings and Review | List | Sort | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Ratings and Review | List | Filter | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
Ratings and Review | View Ratings and Review | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Ratings and Review | Hide / Unhide Review | [8 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
Ratings and Review | Export Report | [8 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 3
Reports | Generate New Report | Select the type of Report | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 1 | 1 | 1
Reports | Generate New Report | Select Start Date and End Date | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Reports | Generate New Report | Save as Report | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
Reports | List view of Previous Reports | Search | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
Reports | List view of Previous Reports | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
Reports | List view of Previous Reports | View Report | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
Reports | List view of Previous Reports | Download Report | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Reports | Operational Reports | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
GPS Tracking | Search and Filter | [8 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
GPS Tracking | List of Units / Assets | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 3 | 3
GPS Tracking | View Details | Map View | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
GPS Tracking | View Details | View Location History with time stamp | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
Shift Management | Shifts List | Shift List | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 3 | 3
Shift Management | Shifts List | Search, Sort and Filter | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 2
Shift Management | Shifts List | View Shift Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 2
Shift Management | Shifts List | Edit Shift Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 2 | 2
Shift Management | Shifts List | Delete Shift + Confirmation | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Shift Management | Shift Creation | Assign unique Shift Names | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
Shift Management | Shift Creation | Define shift timings (start and end time) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 1 | 1 | 0
Shift Management | Shift Creation | Add Employees | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 3
Shift Management | Shift Reports | Employee Job Data (Shift wise) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 5 | 5
Shift Management | Roster Management | Generate visual shift rosters (calendar view) | [7 empty] | Simple | Must Have
Shift Management | Roster Management | Auto-schedule based on predefined rules | [7 empty] | Simple | Must Have
Shift Management | Roster Management | Approve or reject shift swap/reassignment requests | [7 empty] | Simple | Must Have
Shift Management | Attendance Tracking | Employee List | [7 empty] | Simple | Must Have
Shift Management | Attendance Tracking | View check-ins and check-outs | [7 empty] | Simple | Must Have
Shift Management | Attendance Tracking | Monitor break durations | [7 empty] | Simple | Must Have
Shift Management | Attendance Tracking | Flag late arrivals or early departures | [7 empty] | Simple | Must Have
Prototype | [9 empty] | Simple | Must Have | [5 empty] | 21
Non-Functional | DB Design | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 34

## Employee App - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login | Email + Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 |  | 0 | 0 | 0
Login | Forgot Password | Email Verification | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Login | Forgot Password | Set New Password | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
My Tasks | List View | List - Upcoming ¦ In- Progress ¦ Paused ¦ Completed ¦ Cancelled | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
My Tasks | List View | Search | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
My Tasks | List View | Sort | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Tasks | List View | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 1 | 2
My Tasks | View Task Details | View the Service Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 3
My Tasks | View Task Details | Request for Tools or Equipment for a Task | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 2
My Tasks | View Task Details | Chat with Customer |  |  | Admin side chat is completed |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 2
My Tasks | Status Actions | To Do (By Default) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 3
My Tasks | Status Actions | In Progress | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
My Tasks | Status Actions | Pause | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
My Tasks | Status Actions | Completed | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 0 | 0 | 0
My Tasks | Status Actions | Cancel | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
My Tasks | Track Travel Time | Check In | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 2 | 2
My Tasks | Track Travel Time | Check out | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 1 | 1 | 1
My Tasks | Track Travel Time | GPS Tracking should be enabled | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
My Tasks | Post Completion | Generate Invoice | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 5
My Tasks | Post Completion | View Invoice | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 3
My Tasks | Post Completion | Download Invoice | [7 empty] | Simple | Must Have | [5 empty] | 1 | 3 | 2 | 0
My Tasks | Create Inspection Report for Respective Tasks | Select Inspection Form from templates |  |  | Design : We have considered 2 templates |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Tasks | Create Inspection Report for Respective Tasks | Add all the details | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 1
My Tasks | Create Inspection Report for Respective Tasks | Attach the images | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 5 | 3 | 3
My Tasks | Create Inspection Report for Respective Tasks | Save or Publish (Once published, Display to User and Admin) | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
My Tasks | Create Inspection Report for Respective Tasks | Should be able to make the edits | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 1
My Tasks | Create Inspection Report for Respective Tasks | Delete the report | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Tasks | Create Inspection Report for Respective Tasks | Prepare an estimation document | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 2
My Tasks | Create Inspection Report for Respective Tasks | Send it for Customer Approval | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
My Schedule | Current Week view | By default, display current date tasks | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
My Schedule | Current Week view | View task details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
My Schedule | Current Week view | Chat with Customer | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 2
In App Messaging | Chat with Customer related to task | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 1
In App Messaging | Conversation Threads (History) | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 2 | 3
In App Messaging | Conversation Screen | Add Text | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 0 | 0 | 0
In App Messaging | Conversation Screen | Add Attachment | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
In App Messaging | Send | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Tools | List - My Tools ¦ Requested ¦ Rejected ¦ Cancelled | List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 2 | 2
My Tools | List - My Tools ¦ Requested ¦ Rejected ¦ Cancelled | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 1
My Tools | List - My Tools ¦ Requested ¦ Rejected ¦ Cancelled | Sort | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Tools | List - My Tools ¦ Requested ¦ Rejected ¦ Cancelled | Filter | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
My Tools | View Tool details | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 3 | 3
My Tools | Actions | Cancel the Request for Tool | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
My Tools | Actions | Return the tools after job | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 1
My Tools | Add new request for tool | Search tools | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
My Tools | Add new request for tool | Select the task for which tool is required | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
My Tools | Add new request for tool | Additional Notes | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 1 | 1 | 0
My Tools | Add new request for tool | Send Request | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
My Transactions | [9 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 3 | 5
Automated Reminders | [9 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 3 | 3 | 5
Profile | View Profile Details | Name, Email, Phone Number | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Profile | View Profile Details | View Password | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Profile | View Profile Details | Change Password | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Profile | My Ratings | Ratings List | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
Profile | My Ratings | Search, Sort and Filter | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Profile | My Ratings | View Review details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 2 | 1 | 2
Profile | Customer Support via Whatsapp |  |  |  | Launch WhatsApp directly |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 1
Profile | Language | Arabic | [7 empty] | Simple | Must Have | [5 empty] | 13 | 5 | 1 | 1
Profile | Language | English | [7 empty] | Simple | Must Have | [6 empty] | 5 | 1 | 1
Profile | Logout | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
My Documents in Units/Assets | Search | [8 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
My Documents in Units/Assets | Units List | View Unit Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Documents in Units/Assets | Units List | View Location (Integrate with Maps) | [7 empty] | Simple | Must Have | [6 empty] | 2 | 3 | 2
My Documents in Units/Assets | View Folder within Unit | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Documents in Units/Assets | View Documents | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 2 | 1 | 2
My Documents in Units/Assets | Download Document | [8 empty] | Simple | Must Have | [6 empty] | 1 | 2 | 0
Prototype | [9 empty] | Simple | Must Have | [5 empty] | 21 | 0 | 0 | 0
Tab Responsive | [9 empty] | Simple | Must Have | [5 empty] | 55 | 34 | 0 | 0
Mobile Responsive | [9 empty] | Simple | Must Have | [5 empty] | 34 | 34 | 0 | 0

## Integration - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Oracle ERP with Units Sales | [9 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 13
Spare Parts Stock & Price check | [9 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 8
Garage Transfers by Parts | [9 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 8
Customer Credit Limit / Outstandining balances checks and subsequent Accounting | [9 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 8
GBFT transactions | [9 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 8
Payment Gateway Integration |  |  |  |  | Stripe Payment Gateway |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 5 | 13

## Customer App - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Customer App - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Admin Panel - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Admin Panel - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Employee App - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Employee App - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Integration - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Integration - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have