## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 40
Deployment | 0
Overall
Team Size
Name | Role | Count
Fe | SSE | 2
Fe | SE | 3
Be | SSE | 0
Be | SE | 0
Ux | UIUX_DESIGNER | 0
Team Hours
Team | Hr / Day
ba | 3
lead | 4
qa | 8
uiux_ba | 0
uiux_lead | 0
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
Chanced Web App | Chanced Web App - Summary
Sub Total

## Chanced Web App - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
App setup | [9 empty] | Simple | Must Have | [6 empty] | 89 | 0 | 0
Layout setup | [9 empty] | Simple | Must Have | [6 empty] | 13 | 0
Guest - Homepage | Live Winners | [8 empty] | Simple | Must Have | [6 empty] | 21 | 3
Guest - Homepage | Featured Games |  | Animation | [7 empty] | Must Have | [6 empty] | 34 | 3
Guest - Homepage | Slot Games | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 13 | 3 | 0
Guest - Homepage | New Games |  | Animation | [7 empty] | Must Have |  |  |  |  | 0 | 0 | 8 | 3 | 0
Guest - Homepage | Banner | [9 empty] | Must Have | [6 empty] | 13 | 3
Guest - Homepage | Testimonials | [9 empty] | Must Have | [6 empty] | 34 | 5
Guest - Homepage | Footer | About Chanced | [7 empty] | Simple | Must Have | [6 empty] | 2 | 0
Guest - Homepage | Footer | Quick Links | [7 empty] | Simple | Must Have | [6 empty] | 3 | 0
Guest - Homepage | Footer | Contact Info | [7 empty] | Simple | Must Have | [6 empty] | 1 | 0
Guest - Homepage | Footer | Copyright | [7 empty] | Simple | Must Have | [6 empty] | 1 | 0
Guest - Homepage | Footer | Social Media Links | [7 empty] | Simple | Must Have | [6 empty] | 3 | 0
Guest - Homepage | Footer | Back to Top | [7 empty] | Simple | Must Have | [6 empty] | 3 | 0
Guest - Homepage | Payment Method Info | [9 empty] | Must Have | [6 empty] | 21 | 0
Guest - Homepage | Live Dealers | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 8 | 3 | 0
Guest - Homepage | Header | Search Bar | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
Guest - Homepage | Header | Login | [7 empty] | Simple | Must Have | [6 empty] | 2 | 3
Guest - Homepage | Header | Sign up | [7 empty] | Simple | Must Have | [6 empty] | 2 | 3
Guest - Homepage | Gold Coins Signup Bonus Timer |  | This seems different than Punt | [7 empty] | Must Have | [6 empty] | 13 | 3
Guest - Homepage | Game Categories | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Guest - Homepage | Information section |  | 4 images. I am unsure on the animation here. | [6 empty] | Simple | Must Have | [6 empty] | 34 | 3
Guest - Homepage | Spin the Wheel & win |  | Animation Expected | [6 empty] | Simple | Must Have | [6 empty] | 34 | 5
Guest - Homepage | Hero Section | [8 empty] | Simple | Must Have | [6 empty] | 34 | 3
Register | Set Password Screen | Checkbox - Referral Code | If checked, an Input Field should appear, currently not in the Figma. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2
Register | Set Password Screen | Continue | [7 empty] | Simple | Must Have | [6 empty] | 2 | 0
Register | Set Password Screen | Checkbox - Terms & conditions Acceptance | [7 empty] | Simple | Must Have | [6 empty] | 2 | 0
Register | Set Password Screen | Enter Age | [7 empty] | Simple | Must Have | [6 empty] | 5 | 2
Register | Set Password Screen | Set password | [7 empty] | Simple | Must Have | [6 empty] | 3 | 0
Register | Sign In Button |  | Redirect to Login Form | [6 empty] | Simple | Must Have | [6 empty] | 3 | 0
Register | Back | [8 empty] | Simple | Must Have | [6 empty] | 3 | 0
Register | Basic Details | First & Last Name | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2
Register | Basic Details | Select Country, State / Province | Search + Select Country and show states/ Province based on the selection | [6 empty] | Simple | Must Have | [6 empty] | 3 | 2
Register | Basic Details | Recaptcha | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
Register | Basic Details | Username | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2
Register | Basic Details | Email | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2
Register | Onboarding Screens |  | 4 different cards | [6 empty] | Simple | Must Have | [6 empty] | 21 | 5
Register | Social Login | Complete your profile | Username, DOB, Country & State | [6 empty] | Simple | Must Have | [6 empty] | 13 | 5
Register | Welcome Screen | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Sign In | Sign up Button |  | Redirection to Sign up Form | [6 empty] | Simple | Must Have | [6 empty] | 3 | 0
Sign In | Forgot Password | Enter email | After email verification, a password reset link sent on the email id. | [6 empty] | Simple | Must Have | [6 empty] | 3 | 3
Sign In | Forgot Password | Reset Password Screen | Password Rules not in Figma. Once Password updated, success message + user redirected to Login screen. | [6 empty] | Simple | Must Have | [6 empty] | 8 | 5
Sign In | Social Sign in | Gmail, Twitch & Facebook | Dependent on Punt's team | [6 empty] | Simple | Must Have | [6 empty] | 3 | 8
Sign In | Email & Password | [8 empty] | Simple | Must Have | [6 empty] | 8 | 8
Logged in Homepage | Tutorial/ How it works |  | 13 screens with cross | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3
Logged in Homepage | Progress & Benefits |  | Live, Week & 24 h | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3
Logged in Homepage | Hero Section | CTA | View Details / Learn More - Need to check on its redirection. | [6 empty] | Simple | Must Have | [6 empty] | 21 | 3
Logged in Homepage | Header | Search Bar | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2
Logged in Homepage | Header | Wallet | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2
Logged in Homepage | Header | GC & SC Balance | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2
Logged in Homepage | Header | Notification | [7 empty] | Simple | Must Have | [6 empty] | 2 | 0
Logged in Homepage | Header | Settings | [7 empty] | Simple | Must Have | [6 empty] | 1 | 0
Logged in Homepage | Header | Profile | [7 empty] | Simple | Must Have | [6 empty] | 1 | 0
Logged in Homepage | Featured Games with Animation | Add to Favourites | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
Logged in Homepage | Featured Games with Animation | Horizontal Scroll | [7 empty] | Simple | Must Have | [6 empty] | 21 | 3
Logged in Homepage | New Games |  | Horizontal scroll + View All. Need to confirm on Animation. | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3
Logged in Homepage | Quick Buy |  | Arrows to move horizontally | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3
Logged in Homepage | Games | Game Categories | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
Logged in Homepage | Games | Game Listing | [7 empty] | Simple | Must Have | [6 empty] | 13 | 5
Logged in Homepage | Trending Slots | [8 empty] | Simple | Must Have | [6 empty] | 13 | 3
Logged in Homepage | Providers | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Logged in Homepage | Challenges | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Logged in Homepage | Refer and Invite | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Logged in Homepage | Leaderboard | Timer | [7 empty] | Simple | Must Have | [5 empty] | 0 | 21 | 3
Logged in Homepage | Progressive Jackpot |  | Animations Expected | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3
Logged in Homepage | Live Winners & filters | Sticking to Top after scroll | [7 empty] | Simple | Must Have | [6 empty] | 13 | 3
Logged in Homepage | Live bets |  | Need UI/ Designs for it | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3
Account | My Profile | [8 empty] | Simple | Must Have | [6 empty] | 2 | 0 | 0
Account | Logout | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Account | Affiliate | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Account | VIP | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Account | Settings | [8 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0
Identity Verification | [9 empty] | Simple | Must Have | [6 empty] | 21 | 8
My Profile | Profile | Overview | Refer to Overview Module | [6 empty] | Simple | Must Have | [6 empty] | 3 | 3
My Profile | Profile | Logout | [7 empty] | Simple | Must Have | [6 empty] | 2 | 2
My Profile | Profile | VIP progress bar | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2
My Profile | Profile | Total won | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2
My Profile | Profile | Total Wagered | Need to check | [6 empty] | Simple | Must Have | [6 empty] | 2 | 2
My Profile | Settings | Private Mode | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Profile | Settings | Change Password | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Profile | Settings | Change Gravatar | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
My Profile | Settings | Verify email | [7 empty] | Simple | Must Have | [6 empty] | 3 | 5
My Profile | Settings | Update email | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
My Profile | Self Assessment |  | Static text and links | [6 empty] | Simple | Must Have | [5 empty] | 0 | 5 | 3
My Profile | Overview | Redeem Bonus Code | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Profile | Overview | Most Played | Horizontal scroll with arrows | [6 empty] | Simple | Must Have | [6 empty] | 8 | 5
My Profile | Overview | Transactions | Deposits/ Withdrawals | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3
My Profile | Overview | Pagination | User can select how many records to show per page. | [6 empty] | Simple | Must Have | [6 empty] | 3 | 3
My Profile | Responsible Social Game Play |  | Static text and links | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Profile | Recognise the Signs |  | Static text and links | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3
Wallet | Top-up | [8 empty] | Simple | Must Have | [6 empty] | 21 | 21
Wallet | Buy Bundle | [8 empty] | Simple | Must Have | [6 empty] | 21 | 34
Wallet | Redeem | Verification checks | [7 empty] | Simple | Must Have | [6 empty] | 55 | 21
Wallet | Redeem | Redeem flow | [7 empty] | Simple | Must Have | [6 empty] | 21 | 21
Wallet | Daily Bonus | [8 empty] | Simple | Must Have | [6 empty] | 34 | 8
Challenges | Mine | [8 empty] | Simple | Must Have | [6 empty] | 2 | 2
Challenges | Load More | [8 empty] | Simple | Must Have | [6 empty] | 3 | 3
Challenges | All | [8 empty] | Simple | Must Have | [6 empty] | 13 | 3
Challenges | Completed | [8 empty] | Simple | Must Have | [6 empty] | 2 | 2
Challenges | Search, Sort & filters | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2
Refer a Friend | Overview | List of Referrals | [7 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 0
Refer a Friend | Overview | Create & View Campaigns | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 0
Refer a Friend | Overview | Referral Stats | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3 | 0
Refer a Friend | Overview | Copy Referral Link | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 0
Refer a Friend | Funds | Withdraw Available commission | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3 | 0
Refer a Friend | Funds | Funds Balance | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 0
Refer a Friend | Funds | Total Redeemed | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 0
Refer a Friend | Campaigns | Create Campaigns | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3 | 0
Refer a Friend | Campaigns | View Existing Campaigns | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 0
Refer a Friend | New Referral Bonus |  | Static text & images | [6 empty] | Simple | Must Have | [6 empty] | 5 | 5 | 0
Refer a Friend | Affiliate referral | [8 empty] | Simple | Must Have | [6 empty] | 5 | 8
Search | Search Results View | [8 empty] | Simple | Must Have | [6 empty] | 13 | 5
Search | Search suggestions | Clear all | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
Games | Game Detail Page | Featured Games | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
Games | Game Detail Page | Iframe load | [7 empty] | Simple | Must Have | [6 empty] | 5 | 13
Games | Search, sort & filters | [8 empty] | Simple | Must Have | [6 empty] | 5 | 5
Games | Game Listing based on Category selected | [8 empty] | Simple | Must Have | [6 empty] | 13 | 5
Games | Load More | [8 empty] | Simple | Must Have | [6 empty] | 3 | 3
Games | Mark as Favourite | Add/ Remove | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
Games | All games | [8 empty] | Simple | Must Have | [6 empty] | 34 | 13
My Game Play | Games Stats | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2
My Game Play | Most Popular | Add to Favourites | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Game Play | Game History | View Game history based on selected Category | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3
My Game Play | Game History | Load More | [7 empty] | Simple | Must Have | [6 empty] | 3 | 3
Notifications | Close | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2
Notifications | Category Filters | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Notifications | List of notifications | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3
Notifications | Sort by | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2
Notifications | Status Filters | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2
Notifications | Mark All as Read | [8 empty] | Simple | Must Have | [6 empty] | 2 | 2
VIP Club | VIP Progress bar and rank | [8 empty] | Simple | Must Have | [6 empty] | 3 | 3 | 0
VIP Club | VIP Club ranks info |  | Horizontal scroll : 12 ranks | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3 | 0
VIP Club | Stats | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 0
VIP Club | Claim Rakeback | [8 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 0
VIP Club | Static text & Images | [8 empty] | Simple | Must Have | [6 empty] | 8 | 2
Promotions | Latest Promotions | Promotion Detail Page | [7 empty] | Simple | Must Have | [6 empty] | 21 | 3
Promotions | Different type of Promotions |  | Casino, sports | [6 empty] | Simple | Must Have | [6 empty] | 13 | 3
Favourites | List of games marked as Favourites | [8 empty] | Simple | Must Have | [6 empty] | 8 | 5
Favourites | Search, Sort & Filter | [8 empty] | Simple | Must Have | [6 empty] | 3 | 3
Live Support | [9 empty] | Simple | Must Have | [6 empty] | 5 | 5
Live Chat | [9 empty] | Simple | Must Have | [6 empty] | 13 | 8
Recent Games | [9 empty] | Simple | Must Have | [6 empty] | 8 | 5
404 Page Not Found | [9 empty] | Simple | Must Have | [6 empty] | 13 | 0
Raffle | Upcoming Tickets | [8 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 0
Raffle | View | [8 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 0
GTM Events |  |  | Need Confirmation | [6 empty] | Simple | Must Have | [6 empty] | 0 | 21 | 0
Static Info | CAP | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Terms & conditions | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Payment FAQ | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Sweeps Rule | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Privacy Policy | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Responsible Gameplay | [8 empty] | Simple | Must Have | [6 empty] | 5 | 2
Static Info | Responsible Social Policy | [8 empty] | Simple | Must Have
Loading UI |  |  | 5 Screens and Overall Animation | [6 empty] | Simple | Must Have | [6 empty] | 34 | 0
Performance Optimisation | [9 empty] | Simple | Must Have | [6 empty] | 55 | 89
SonarQube Fixes | [9 empty] | Simple | Must Have | [6 empty] | 8 | 34
Partner landing pages | [9 empty] | Simple | Must Have | [6 empty] | 34 | 8
Punt Tasks | Facebook Sign in | [8 empty] | Simple | Must Have | [6 empty] | 3 | 5
Punt Tasks | Live Bets | [8 empty] | Simple | Must Have | [6 empty] | 13 | 5
Punt Tasks | Races Dashboard Changes | [8 empty] | Simple | Must Have | [6 empty] | 21 | 5
Mobile & Tablet Responsive | [9 empty] | Simple | Must Have | [6 empty] | 55 | 34
Cookie Management |  |  | Need Confirmation | [6 empty] | Simple | Must Have | [6 empty] | 0 | 21 | 0
SEO & Accessibility management | [9 empty] | Simple | Must Have | [6 empty] | 8 | 21
Feature Flag | [9 empty] | Simple | Must Have | [6 empty] | 34 | 55
Design system components | Button | [8 empty] | Simple | Must Have | [6 empty] | 21 | 0
Design system components | TextInput | [8 empty] | Simple | Must Have | [6 empty] | 21 | 0
Design system components | Dropdown | [8 empty] | Simple | Must Have | [6 empty] | 8 | 0
Design system components | Search | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Checkbox | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Switch | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Toast | [8 empty] | Simple | Must Have | [6 empty] | 13 | 0
Design system components | Game Card | [8 empty] | Simple | Must Have | [6 empty] | 34 | 8
Design system components | Modal | [8 empty] | Simple | Must Have | [6 empty] | 13 | 0
Design system components | MultipleItem Picker | [8 empty] | Simple | Must Have | [6 empty] | 8 | 0
Design system components | Challenge card | [8 empty] | Simple | Must Have | [6 empty] | 8 | 0
Design system components | Bundle card | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Swiper | [8 empty] | Simple | Must Have | [6 empty] | 21 | 0
Design system components | Filter | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Timer | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | SortBy | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Progressbar | [8 empty] | Simple | Must Have | [6 empty] | 5 | 0
Design system components | Tabs | [8 empty] | Simple | Must Have | [6 empty] | 8 | 0
Design system components | Pagination | [8 empty] | Simple | Must Have | [6 empty] | 13 | 0
Design system components | Step progress | [8 empty] | Simple | Must Have | [6 empty] | 21 | 0
Design system components | Winners Card | [9 empty] | Must Have | [6 empty] | 5 | 0
Design system components | Country/State Picker | [9 empty] | Must Have | [6 empty] | 13 | 0
Design system components | Banners | [9 empty] | Must Have | [6 empty] | 8 | 0
Design system components | RichTextContainer | [9 empty] | Must Have | [6 empty] | 13 | 0
Design system components | Table | [9 empty] | Must Have | [6 empty] | 8 | 0
Design system components | Phone number input | [9 empty] | Must Have | [6 empty] | 8 | 0
Design system components | Daily Bonus Card | [9 empty] | Must Have | [6 empty] | 5 | 0
Design system components | Campaign Card | [9 empty] | Must Have | [6 empty] | 5 | 0
Design system components | VIP Club Rank Card | [9 empty] | Must Have | [6 empty] | 8 | 0
Design system components | Accordion | [9 empty] | Must Have | [6 empty] | 5 | 0
Design system components | Promotion Card | [9 empty] | Must Have | [6 empty] | 5 | 0
Design system components | Sidebar | [9 empty] | Must Have | [6 empty] | 21 | 0
Design system components | Bottom Tabs | [9 empty] | Must Have | [6 empty] | 13 | 0
Design system components | Stylebook creation | [9 empty] | Must Have | [6 empty] | 34 | 0

## Chanced Web App - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Chanced Web App - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have