## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 0
Deployment | 144
Overall
Team Size
Name | Role | Count
Fe | SE | 2
Fe | SSE | 1
Be | SSE | 1
Be | SE | 1
Ux | UIUX_DESIGNER | 2
Team Hours
Team | Hr / Day
ba | 3
lead | 2
qa | 4
uiux_ba | 2
uiux_lead | 0
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
End User | End User - Summary
Admin | Admin - Summary
Sub Total

## End User - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Non Functional | Boilerplate | [8 empty] | Simple | Must Have | [6 empty] | 21 | 8 | 0
Non Functional | Integrate - Health Provider (try vital) | [8 empty] | Simple | Must Have | [6 empty] | 5 | 8 | 34
Splash Screen |  |  | The splash screen displays the app logo with smooth animation, creating a seamless and engaging first impression while loading essential data. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 0
Sign In | Social Media Sign In | Apple (IOS) | [7 empty] | Simple | Must Have | [6 empty] | 2 | 5 | 5
Sign In | Social Media Sign In | Google (Android, IOS) | [7 empty] | Simple | Must Have | [6 empty] | 2 | 3 | 3
Sign In | User Onboarding | Enter personal details | Name, Date of Birth, height, weight, sex, select activity level (mostly sedentary, moderately active, very active), exercise frequency (1,2,3,4,5,6,7,7+), pre-existing conditions (Pre-diabetes / diabetes, high cholesterol / triglycerides, high blood pressure, heart disease, none), health goal (Lose weight, Get stronger, Improve overall fitness, Improve biomarkers, Longevity), motivation | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 5
Sign In | User Onboarding | View target calories and macronutrient breakdown | End user should be able to see the target calories and macronutrients based on the questionnaire. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 3
Dashboard | Onboarding screen |  | This will have the basic information about the platform | [6 empty] | Simple | Must Have | [6 empty] | 13 | 5 | 21
Dashboard | View Today's Highlight |  | Show one daily highlight at the top of the dashboard page. For initial usage, we can show something like “Log meals for 5 days to start generating insights”, “log meals for 3 more days to start generating insights”, etc. | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 21
Dashboard | View meal logging streak (7-day view) |  | View the status of the meals logged in the last 7 days on the card that displays the day’s logged calories & macros. The status is shown in three colors: dark for all meals logged, lighter for some meals logged, and grey for no meals logged. Users can see their daily meal logging status (fully logged, partially logged, not logged) based on colour | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 13
Dashboard | View details of today’s meals and previous days’ meals | View detailed view of the calories by meal | [7 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 5
Dashboard | View calories and macronutrients for the day |  | Show the current day’s logged calories & macros. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 13
Dashboard | Chat Interface |  | Launch the chat interface by tapping on the chat icon on the dashboard OR by swiping down on any screen in the app | [6 empty] | Simple | Must Have | [6 empty] | 8 | 5 | 5
Chat Interface | Meal Logging | Log via text chat | The user should be able to log a meal with natural language. For e.g. “I had toast and eggs for breakfast”. The app should calculate the calories & macronutrients for this, store it, and display it to the user Use NLP or LLM with few-shot examples for intent recognition. Parse text for meal details (type, contents, quantity). Connect with Nutrionix API for calories & nutrition, storing data locally for reuse. Use Gemini 2.0 or GPT-4o for chat. Store meal details in user profile. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 55
Chat Interface | Meal Logging | Log via voice chat | The user should be able to log a meal with natural language. For e.g. “I had toast and eggs for breakfast”. The app should calculate the calories & macronutrients for this, store it, and display it to the user TTS and STT for voice chat. We can use APIs from Google. | [6 empty] | Simple | Must Have | [6 empty] | 21 | 55 | 55
Chat Interface | Meal Logging | Log via image upload | Launch the camera within the app to allow the user to take a picture | [6 empty] | Simple | Must Have | [6 empty] | 3 | 5 | 5
Chat Interface | Meal Logging | Food Image Recognition | Parse the image and show details to the user in the chat interface to confirm that we got it right. Once the user confirms, provide details of calories & macronutrients to the user. | [6 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 21
Chat Interface | Meal Logging | Bulk Meal Logging | The user should be able to log multiple meals at once. E.g., “I had toast for breakfast, pasta for lunch, and rice & chicken for dinner today.” | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 13
Chat Interface | Meal Logging | Repeat Meal Logging | Allow the user to reference meals within the last 1 week. When they do, retrieve it and log it. For e.g., I should be able to say, “I had the same breakfast as yesterday”. I should also be able to pick from a list of common meals from the chat window. | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 8
Chat Interface | Meal Logging | Follow-up Questions | If there is insufficient information, the chat interface should auto prompt a question. For e.g. “How many pieces of toast and eggs did you eat?” In general, we should ask at most two follow-up questions to the user, so as to not make the logging experience long. | [6 empty] | Simple | Must Have | [6 empty] | 3 | 3 | 21
Chat Interface | Meal Logging | Share meal satisfaction level | After the user logs a meal, ask how they felt and provide options: “How did you feel after eating this meal?” and provide 5 options: Energized, Satisfied, Neutral, Sluggish, Bloated / Unwell. | [6 empty] | Simple | Must Have | [6 empty] | 2 | 2 | 13
Chat Interface | Meal Logging | Meal History Query | Ask past meal details (e.g., "What did I eat for lunch last Monday?") | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 21
Chat Interface | Meal Logging | Trend Analysis Queries | Compare past meal logs (e.g., "Is my protein intake increasing?") | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 34
Chat Interface | Meal Summary | View calories and macronutrients | [7 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 13
Chat Interface | Meal Summary | View meal details | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 8
AI Health Coach | Ask General Health Questions | View Footnotes | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 34
AI Health Coach | Ask Nutrition Questions | View footnotes | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 21
AI Health Coach | Ask Personalized Health Queries |  | Users can ask personalized questions based on their own data. | [6 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 21
AI Health Coach | Ask Logged Meals Questions | View Meal Info | [7 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 21
AI Health Coach | Ask Trend or analysis based Questions |  | Ask a trend or analysis questions, such as, “Is my protein intake going up?”, “On average, how many calories do I consume at dinner?” | [6 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 21
User Profile | View & Edit Profile | View collected profile data | [7 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 3
User Profile | View & Edit Profile | Edit profile data | [7 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
User Profile | View & Edit Profile | View recalculated calorie & macronutrient targets | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 5
User Profile | Report Issues | Enter app-related issues via a text field | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
User Profile | Report Issues | Send issue via email | The issue is sent via email to the client's email ID for now | [6 empty] | Simple | Must Have | [6 empty] | 1 | 0 | 0
User Profile | Overview | View Best Streak | Total number of days for continuous meal logging | [6 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 8
User Profile | View Today Key Stats (Daily log, calorie & macronutrient breakdown) | [8 empty] | Simple | Must Have | [6 empty] | 8 | 3 | 13
User Profile | Logout |  | This will allow the user to log out of the platform | [6 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1

## Admin - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Non Functional | Boilerplate | [8 empty] | Simple | Must Have | [6 empty] | 13 | 8 | 21
Non Functional | ERD | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 34
Login | Email & Password | [8 empty] | Simple | Must Have | [6 empty] | 5 | 3 | 5
Login | Forgot Password | OTP Verification | [7 empty] | Simple | Must Have | [6 empty] | 5 | 5 | 5
Dashboard | Number of Users | [8 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 8
Dashboard | Daily active Users | [8 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 0
Dashboard | Number of meals logged | [8 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 0
Dashboard | Mode of log (Image, Voice, text) | [8 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 0
Dashboard | View System performance metrics | API calls | [7 empty] | Simple | Must Have | [6 empty] | 5 | 5 | 8
Dashboard | View System performance metrics | Errors | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Dashboard | View System performance metrics | Response times | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Dashboard | View System performance metrics | Latency | [7 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Profile | View details |  | Admin should be able to view his details | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 5
Profile | Edit details |  | Admin should be able to update his details | [6 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 5
Profile | Logout |  | Admin should be able to logout | [6 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 0

## End User - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
End User - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Admin - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Admin - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have