## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 40
Deployment | 40
Overall
Team Size
Name | Role | Count
Fe | SE | 2
Fe | SSE | 1
Be | SSE | 1
Be | SE | 1
Ux | UIUX_DESIGNER | 0
Team Hours
Team | Hr / Day
ba | 2
lead | 2
qa | 4
uiux_ba | 3
uiux_lead | 2
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
Existing Web (Trash) | Existing Web (Trash) - Summary
Website (New) | Website (New) - Summary
Sub Total

## Existing Web (Trash) - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Home | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
About us | Who are we? | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
About us | What we do | Broadcasting and On Demand | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
About us | What we do | Online Safety | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
About us | What we do | Media Development | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Broadcasting and On Demand | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Online Safety | Main Page | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Online Safety | Expand and Collapse Views | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Media Development | Main Page | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Media Development | Expand and Collapse Views | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Online Safety | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Designation Notices | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
News | Grid View | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
News | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Careers | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Publications | List View | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Publications | Search ¦ Filter | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Publications | Download on click | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Change Language | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Contact us | Contact Information | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Contact us | Social Links : LinkedIn ¦ Twitter ¦ Instagram | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
BAI | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Cookies (Check description) |  |  | https://www.bai.ie/en/about-us/cookie-policy/ | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Data Protection | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Freedom of Information | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Sign up for New updates | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
FAQs | List view | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
FAQs | Expand and Collapse | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Social Links : LinkedIn ¦ Twitter ¦ Instagram | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
Manage Consent | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0

## Website (New) - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Home |  |  | Header, Footer and role based view for content | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 21 | 21
About us | Who are we? | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
About us | What we do | Broadcasting and On Demand | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 13 | 8 | 8
About us | What we do | Online Safety | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
About us | What we do | Media Development | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
About us | Newsletter Sign up |  | Only the email is captured and stored. The other mailing feature is covered in a separate module. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
News | Grid View | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
News | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
News | Search |  | Search in three categories - news, research, publications | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 13 | 13 | 13
News | Share |  | share in social media accounts | [7 empty] | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 0
Industry :: About Us [In-depth details across Modules] | Regulations |  | Different regulations - information via different docs, print feature | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 21 | 8
Industry :: About Us [In-depth details across Modules] | Complaints |  | Only the main listing. Details are covered in different module | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Industry :: About Us [In-depth details across Modules] | Broadcast licensing – applications / requirements. |  | Form handling, PDF viewer | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 21 | 8
Industry :: About Us [In-depth details across Modules] | Register of Media Service Providers | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Industry :: About Us [In-depth details across Modules] | Media development activities | Funding Schemes | Listing and viewer of items | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Industry :: About Us [In-depth details across Modules] | Media development activities | Learning | Listing and viewer of items | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Industry :: About Us [In-depth details across Modules] | Media development activities | Research | Listing and viewer of items | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Industry :: About Us [In-depth details across Modules] | Levy Order | Information | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Levy Order | Procedure | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Levy Order | Templates | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Information | Trusted Flaggers | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Information | Nominated Bodies | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Information | Vetted Research | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Industry :: About Us [In-depth details across Modules] | Other Info | Tools | Only listing and links | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Industry :: About Us [In-depth details across Modules] | Other Info | Resources | Only listing and links | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Industry :: About Us [In-depth details across Modules] | Other Info | Research | Only listing and links | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Complaints Portal | Register a new complaint | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Complaints Portal | List of Complaints | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Complaints Portal | View Complaint Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Complaints Portal | Delete Complaint | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Careers | Main Page for Careers | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Careers | Job Openings |  | Listing with search | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 13 | 8
Careers | View Job Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Careers | Apply for Job - Navigating to salesforce |  | https://salesforce-eu.123formbuilder.com/form-71304/cnam-higher-executive-officer-funding-schemes-media-landscape | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Careers | Sign up for Job Alerts |  | Only signup information captured. Alerts to be handled separately. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Publications | List View | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Publications | Search ¦ Filter | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Publications | Download on click | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 8
Mandatory / Legal content | Site map | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Mandatory / Legal content | Cookie / Privacy / Data protection |  | https://www.bai.ie/en/about-us/cookie-policy/ | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 13 | 8 | 8
Mandatory / Legal content | Relevant accessibility information & statements | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 5
Mandatory / Legal content | Terms & Conditions | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Mandatory / Legal content | Freedom of Information / FOI publication scheme (Links in Description) |  | https://www.bai.ie/en/about-us/freedom-of-information/#al-block-1 / https://www.bai.ie/en/foi-publication-scheme/ | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 13 | 8 | 8
Mandatory / Legal content | Change Language :: English and Irish | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 8 | 8
Contact us | Contact Information | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Contact us | Social Links : LinkedIn ¦ Twitter ¦ Instagram | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 5 | 5
Additional Actions Based on Roles | Consumers / Public | Contribute to Relevant Public Consultation | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Additional Actions Based on Roles | Trusted flaggers | Apply for trusted flagger status | Some verification flow might be needed at backend | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 21
Additional Actions Based on Roles | Nominated Bodies | Create Notification | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 8
Additional Actions Based on Roles | Nominated Bodies | View Notification | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Additional Actions Based on Roles | Nominated Bodies | Edit Notification | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Additional Actions Based on Roles | Nominated Bodies | Enable / Disable Notification | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 5 | 5
Additional Actions Based on Roles | Nominated Bodies | Notifications List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Additional Actions Based on Roles | Nominated Bodies | Apply to become Nominated body | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Additional Actions Based on Roles | Students / Researcher | Apply to be Vetted researcher | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Notifications | List | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Notifications | View Notification Details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Social account feeds (home page) |  |  | Considering the two in BAI - twitter and facebook | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 21 | 8
Technical Considerations | Interactive Search Engine | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Technical Considerations | Chat bot - Genesys | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 8 | 0
Technical Considerations | Comprehensive Complaints Portal | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 21 | 21 | 21
Technical Considerations | Integrations | Funding System | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Technical Considerations | Integrations | Contract Management System | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Technical Considerations | Integrations | Online Applications | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Technical Considerations | Integrations | Newsletters Sign up : Email marketing software (MailChimp) | UI already covered in other modules. Backend services to send emails , alerts | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 34
Technical Considerations | Integrations | Recruitment Agencies | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Technical Considerations | Integrations | Secure Data sharing Platform | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 8
Technical Considerations | Integrations | Multimedia Integration | Backend can handled chunked approach and media resolution | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 21 | 21
Technical Considerations | Integrations | Interactive Visual Content | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 55 | 55 | 34
Technical Considerations | Integrations | ReachDesk utility | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 34 | 0
Training guide for internal team | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 34 | 0 | 0
Font selector for viewing | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 8 | 0
Persona creation | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8
Authentication | Login | Forgot password | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 5 | 5
Authentication | Login | Email and password | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 5 | 5 | 5
Authentication | New User - Register | Enter name, email id and password | There can be more fields | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 8 | 8
Authentication | New User - Register | Select Role | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 2
Authentication | New User - Register | Email Authentication | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8
Authentication | Log Out | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 2 | 5 | 5

## Existing Web (Trash) - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Existing Web (Trash) - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Website (New) - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Website (New) - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
NextJS | Strapi | AWS | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have