## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 0
Deployment | 40
Overall
Team Size
Name | Role | Count
Fe | SSE | 0
Fe | SE | 2
Be | SE | 1
Be | SSE | 0
Ux | UIUX_DESIGNER | 2
Team Hours
Team | Hr / Day
ba | 0
lead | 2
qa | 4
uiux_ba | 3
uiux_lead | 2
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
Website | Website - Summary
Sub Total

## Website - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Landing Page (Index Page/Home Page) | Home Page | View Details | Dynamic Contents | [6 empty] | Simple | Must Have |  |  |  |  | 5 | 3 | 5 | 5 | 8
Landing Page (Index Page/Home Page) | Home Page | Buttons redirections | Get Involved & become a member to Membership screen, Team Impact > learn more to Subscription Benefit screen, How to help > Learn More to PU Mates screen | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 5 | 0
Landing Page (Index Page/Home Page) | Home Page | Pop Up Form | Input Field | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 3 | 5 | 5 | 5
Registration / Sign in | [9 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 13 | 13 | 13
NavigationAndContact | Category Buttons |  | Membership, Subscription Benefit, About, Employer, PU Mates, Resources | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0 | 8 | 8 | 0
NavigationAndContact | Search |  | Elastic Search | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0 | 5 | 5 | 0
NavigationAndContact | Contact Us | View Details | Helpline Phone Number, Address, Email ID details, Enquiry Form, Google Map | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 5 | 5 | 0
NavigationAndContact | Contact Us | Google Map Integration | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 8 | 8 | 0
NavigationAndContact | Contact Us | Form- Input Field | Form - Name, email, phone number, address, Support Subject Options drop down, optional message | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 3 | 5 | 0
NavigationAndContact | Contact Us | Support 3rd Party Integration | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0
CommunityAndInformation | Social Media Plugins | Redirection to Social Media Webapp / Landing Page | Outside the application | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 0
CommunityAndInformation | About Us | Employer | Redirection to Employer Screen | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 0
CommunityAndInformation | About Us | PU Mates | Redirection to PU Mates Screen | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 1 | 1 | 0
CommunityAndInformation | About Us | Our Team | Redirection to Our Team Screen | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 1 | 1 | 0
CommunityAndInformation | About Us | Success Stories | Redirection to Success Stories Screen | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 1 | 1 | 0
CommunityAndInformation | Join Us | Contact Us | Redirection to Contact Us Screen | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 2 | 2 | 0
CommunityAndInformation | Join Us | Become A Member | Broken Link View Screen | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 2 | 2 | 0
CommunityAndInformation | Join Us | Subscription Plan | Broken Link View Screen | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 0
CommunityAndInformation | Join Our Mailing List | Input Field | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 1 | 2 | 0
CommunityAndInformation | Join Our Mailing List | Subscribe Button | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 1 | 1 | 2 | 0
CommunityAndInformation | Privacy Policy | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 0
CommunityAndInformation | Terms of Use | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 2 | 2 | 0
Subscription Benefit | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 5 | 5 | 5
Subscription Benefit | Buttons redirections | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 2 | 2 | 0
Assessment Questions | Form (Input Field) |  | Name, Email ID, Phone Number | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 5 | 5
Assessment Questions | List of Questions | Updating response | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 13 | 8 | 8
Assessment Questions | View Result | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 0 | 8 | 8 | 5
Assessment Questions | Membership Recommendation |  | Based on the assessment result | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 8 | 5 | 5
Membership & Payment & calendar | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 8 | 5 | 5
Membership & Payment & calendar | Calendly Calendar Integration | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 3 | 5 | 13 | 8
Membership & Payment & calendar | Checkout and Payment | Payment Gateway | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 3 | 21 | 21 | 13
About | CEO Message | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 2 | 2 | 0
About | CEO Message | Buttons redirections | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 0 | 2 | 2 | 0
About | Our Team | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 2 | 2 | 0
About | Our Team | Buttons redirections | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 5 | 2 | 2 | 0
About | Success Stories | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 2 | 3 | 2 | 0
Employer | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 3 | 2 | 5
Employer | Input Field |  | Form - Name, Email, Phone Number | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 3 | 0
PU Mates | Input Field |  | Form - Name, Email, Phone Number | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 3 | 2 | 0
PU Mates | View Details | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 3 | 3 | 5
Resources | FAQ | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 2 | 8 | 5 | 8
Resources | Blog | View Details | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 3 | 13 | 13 | 13
Resources | Blog | Blog List | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 8 | 8 | 8
Resources | Blog | Categories List | Lifestyle, Senior health, Social Media | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 2 | 8 | 8 | 8
Resources | Blog | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 3 | 8 | 8
Mobile Responsive | [9 empty] | Simple | Must Have |  |  |  |  | 55 | 0 | 21 | 0 | 0
Prototype | [9 empty] | Simple | Must Have |  |  |  |  | 13 | 0 | 0 | 0 | 0
UX Process | [9 empty] | Simple | Must Have |  |  |  |  | 34 | 0 | 0 | 0 | 0
Styleguide | [9 empty] | Simple | Must Have |  |  |  |  | 13 | 0 | 0 | 0 | 0

## Website - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Website - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
NextJS, ReactJS | MySQL, NodeJS | AWS | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have