## Master Summary
Name | Total Hours | Visual Design | Backend | Web Mobile | Wireframe | Sheet Name
Project Management
Team | Overall
UI/UX Lead
UI/UX Review
Design Hours (Wireframe + Visual Design)
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0
Development Hours (Web/Mobile + Backend)
BA
QA
UAT
Lead
Documentation | 120
Deployment | 120
Overall
Team Size
Name | Role | Count
Fe | SSE | 0
Fe | SE | 1
Be | SE | 1
Be | SSE | 2
Ux | UIUX_DESIGNER | 0
Team Hours
Team | Hr / Day
ba | 4
lead | 8
qa | 8
uiux_ba | 0
uiux_lead | 0
Project Development Time Line
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Over All
App Wise Phase Estimation
Name | Sheet Name | Web/Mobile | Backend | Visual Design | Wireframes | Total Hours
End User | End User - Summary
Business Owner | Business Owner - Summary
Admin | Admin - Summary
Sub Total

## End User - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login Flow | Phone number ¦ OTP Verification |  |  |  | Backend scheduler for otp is assumed here, Frontend shadcn lib usage |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 3
Login Flow | Email address verification |  |  |  | backend logic and scheduler for email deliver |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 3
Login Flow | Create Account |  |  |  | backend logic, validation, check for old account, task-queue, etc. |  |  |  |  | Simple | Must Have | [6 empty] | 0 | 0 | 5
Login Flow | Auth guard for all routes + roles management |  |  |  | Auth guard and other auth related setup is assumed here as well |  |  |  |  | Simple | Must Have | [6 empty] | 0 | 0 | 8
Homepage | Select User feedback ¦ Business owner |  |  |  | FE only as navigation |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 0 | 0
Homepage | Display Animation videos |  |  |  | streaming of video file for better performance. If gif is provided, then conversion is required if it has performance effect otherwise no backend required |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 1 | 3
Homepage | View list of Businesses | [8 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Homepage | Search bar | Search success screen |  |  | rate limiting search should be here, frontend will have debounce feature for less network calls |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 1 | 3
Homepage | Make suggestion button | [8 empty] | Simple | Must Have | [6 empty] | 1 | 0 | 0
Suggestion Flow | View business details page |  |  |  | backend api for retrieval, frontend design |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 2
Suggestion Flow | Image banner ¦ Text paragraph | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 0
Suggestion Flow | Toggle to post feedback as anonymous | [8 empty] | Simple | Must Have | [6 empty] | 1 | 0 | 0
Suggestion Flow | View ¦ Select suggestion categories |  |  |  | backend state capture api (maybe replaced with frontend url states) |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 0 | 1
Suggestion Flow | Display category tag upon selection |  |  |  | frontend animation, backend fetch categories |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 0 | 1
Suggestion Flow | Send suggestion |  |  |  | backend message capture in temp database? Not required in mvp but will be good for user to return back to the same step |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 1 | 1
Suggestion Flow | Input the possiblity percentage to return |  |  |  | frontend haptic feedback vibration api implementation, backend capture state |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 0 | 1
Suggestion Flow | Submit response |  |  |  | backend logic to submit response, send an email if required, use schedular to scale here |  |  |  |  | Simple | Must Have | [6 empty] | 1 | 1 | 5
Suggestion Flow | Submit success screen | [8 empty] | Simple | Must Have | [6 empty] | 3 | 0 | 0
Post - Suggestion flow | View all the list of suggestions |  |  |  | reuse the previous components in frontend for quick iteration, backend is same as well to reuse the previous api points to retrieve data |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 2
Post - Suggestion flow | View status of suggestions Delivered ¦ Seen ¦ Acknowledged |  |  |  | . reuse the previous components in frontend for quick iteration edit delete 2. backend is same as well to reuse the previous api points to retrieve data |  |  |  |  | Simple | Must Have | [6 empty] | 1 | 1 | 1
Post - Suggestion flow | View suggestion details page |  |  |  | . reuse the previous components in frontend for quick iteration edit delete 2. backend is same as well to reuse the previous api points to retrieve data |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 2
My Profile |  |  |  |  | backend fetch and change password apis, frontend to remain simple data show and change password feature |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 2 | 5
Testing |  |  |  |  | Devs will be writing the unit testing for their respective end codebase., QA team will be writing the e2e testing for the whole app using Playwright., Backend coverage is assumed to be 100% while the Frontend coverage to be above 75% during the MVP |  |  |  |  | Simple | Must Have | [6 empty] | 89 | 0 | 89
Third party integrations | AWS SNS for SMS verification. | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 21
Third party integrations | AWS SES or Klaviyo for email notifications | [8 empty] | Simple | Must Have | [6 empty] | 0 | 0 | 21
Third party integrations | Segment Tool for CDP: Mixpanel integration OR Just Mixpanel for MVP |  |  |  | analytics should be server side so assumed that for better results, mixpanel is assumed as it has good docs for doing server side tracking, Segment tool will be used if the time permits during the MVP Phase or will be taken later after the MVP |  |  |  |  | Simple | Must Have | [6 empty] | 34 | 8 | 89
Reward points module |  |  |  |  | Backend will have a mapping system in place for mapping action with their respective reward points, Backend will provide the event api point to track those actions as and when they happen to increase the reward points for a user, Frontend will call the API points during the UX based on actions of the user |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 1 | 8

## Business Owner - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login flow |  |  |  |  | assumed most backend logic to be similar to user login with some additional requirements, frontend is different as per our talks with email and password |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 2 | 5
Dashboard | View chart with suggestion count & return percentage |  |  |  | assumed status animation here, backend data fetch assumed, changed design with percentage logic to be used here instead. |  |  |  |  | Simple | Must Have | [6 empty] | 13 | 3 | 5
Dashboard | Inbox view - All suggestions list |  |  |  | complete frontend box with all status states and 3 state pills above with animation, backend apis and proper data format |  |  |  |  | Simple | Must Have | [6 empty] | 8 | 1 | 5
Dashboard | View list of Resolved & Archive suggestions |  |  |  | frontend already built in inbox above, same with backend |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 1 | 1
Dashboard | View suggestion details |  |  |  | backend data retrieval and frontend |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 1
Dashboard | Mark status with Acknowledge ¦ Resolved ¦ Archive |  |  |  | scheduler based backend action if required otherwise direct database update, frontend assumed animated moving of inbox message to either resolve or reject state |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 3
Business Owner contact Form | Input fields - Name ¦ Business name ¦ City ¦ Email | [8 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 5
Business Owner contact Form | Submit button | [8 empty] | Simple | Must Have | [6 empty] | 1 | 0 | 0

## Admin - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | Visual Design Story Points | Frontend Story Points | Integration Story Points | Backend Story Points | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login flow | [9 empty] | Simple | Must Have | [6 empty] | 3 | 0 | 3
Homepage | Search banner |  |  |  | Simple search bar mimicking other search bars, backend search api with limits and offsets |  |  |  |  | Simple | Must Have | [6 empty] | 2 | 1 | 5
Homepage | View list of businesses | Select Customers ¦ Leads |  |  | backend will give the result of the query params here using the API point, frontend will be creating a switch which will insert the query params in the URL here. |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 0 | 3
Homepage | View list of businesses | View Customer List |  |  | sortable data table to be used in the FE and BE will provide the lists |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 1 | 3
Homepage | View list of businesses | View Lead list | [7 empty] | Simple | Must Have | [6 empty] | 5 | 1 | 3
Homepage | View list of businesses | List cards with all its data points | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
Homepage | View list of businesses | Edit form |  |  | Just a UI button here for now |  |  |  |  | Simple | Must Have | [6 empty] | 1 | 0 | 0
Homepage | Add business | View add business form | [7 empty] | Simple | Must Have | [6 empty] | 2 | 0 | 0
Homepage | Add business | Input fields - Business Name ¦ Business Type ¦ Business City ¦ Business logo ¦ Send invite | [7 empty] | Simple | Must Have | [6 empty] | 5 | 2 | 5
Homepage | Add business | Upload Business logo ¦ Business hero image | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 3
Homepage | Add business | Add business ¦ Cancel button | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
Homepage | Add business | Radio button - QR Code |  |  | backend will map the QR code on the fly using the manual ID or automatic creation here |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 1 | 5
Homepage | Add business | Edit business form | [7 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 3
Suggestly Feed | Suggestion analytics | Display days as tags | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 3
Suggestly Feed | Suggestion analytics | Display total suggestions ¦ High quality ¦ Low quality suggestions | [7 empty] | Simple | Must Have | [6 empty] | 3 | 2 | 3
Suggestly Feed | Suggestion feed | Search ¦ Sort | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
Suggestly Feed | Suggestion feed | View list of businesses | [7 empty] | Simple | Must Have | [6 empty] | 5 | 1 | 2
Suggestly Feed | Suggestion feed | Display Date ¦ Business ¦ Sentiment ¦ Status ¦ Category ¦ Action | [7 empty] | Simple | Must Have | [6 empty] | 8 | 1 | 3
Suggestly Feed | Suggestion feed | See suggestion screen | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
QR code management | List |  |  |  | proper paginated data to be provided by the backend |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 1 | 5
QR code management | Card | Download | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 1
QR code management | Card | Copy link | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 1
QR code management | Card | Notes | [7 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 2
Redirect Tool | Settings |  |  |  | redirect settings to be done properly on the backend or NextJS end |  |  |  |  | Simple | Must Have | [6 empty] | 3 | 2 | 8
Redirect Tool | Active listing | List | [7 empty] | Simple | Must Have | [6 empty] | 3 | 1 | 3
Redirect Tool | Active listing | Delete | [7 empty] | Simple | Must Have | [6 empty] | 1 | 1 | 2
Redirect Tool | Active listing | Edit | [7 empty] | Simple | Must Have | [6 empty] | 2 | 1 | 2
My Profile |  |  |  |  | basic data profile with the ability to change the password |  |  |  |  | Simple | Must Have | [6 empty] | 5 | 1 | 5

## End User - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
End User - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Business Owner - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Business Owner - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Admin - Summary
Frontend | Backend | Deployment | General Assumption | Design Min | Fe Max | Fe Min
Development Sheet
Sheet Name
Admin - Dev
App Summary
Name | Must Have | Could Have | Should Have | Will not Have | Overall
UX/UI WireFrame
UX/UI Visual Design
UX/UI Lead
UX/UI Review
UI/UX BA
UI/UX UAT
UI/UX Documentation | 0 | 0 | 0 | 0
Web / Mobile
Backend
Lead
Qa
Ba
UAT
Deployment | 40 | 0 | 0 | 0
Documentation | 40 | 0 | 0 | 0
Total
Development Timeline ( Weeks)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Development Timeline ( Months)
App Name | FE Min | FE Max | BE Min | BE Max | Design Min | Design Max
Must Have
Could Have
Should Have
Will Not Have
Overall
Tech Details
Frontend | Backend | Deployment | General Assumption
Not added yet | Not added yet | Not added yet | Not added yet

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have