## Customer App - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 1.5 | Visual Design Story Points | 2.5 | Frontend Story Points | 381 | Integration Story Points | 162 | Backend Story Points | 4 | 547 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Project Setup |  |  | FE: • React Native setup • Redux setup • Navigation library add • Prettier & ESLint setup • Folder structure finalize • Axios wrapper add • Themeing setup • Font setup • Coding pattern finalize BE: • Nest.js setup • DB setup • EsLint & Prettier setup • Folder structure finalize etc • Coding pattern finalize • Generic error handling | [6 empty] | Simple | Must Have | [5 empty] | 0 | 0 | 0 | 21 | 16 | 0 | 0 | 0 | 0 | 16 | S
Bottom tab navigtaion setup |  |  | • We will be creating basic app layout • Will create common UI components as per design system. eg.: Button, accordion, card, snackbar, loader, input, heading text etc. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 4 | S
Registration & Login | New User - Register | Email password based registration | BE needs to setup the user management service for this. Query: Don't we need to collect user's phone number? |  | For authentication we are considering firebase authentication. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Registration & Login | New User - Register | Terms and Conditions & Privacy link | This will be configured in CMS instead of admin dashboard | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Registration & Login | New User - Register | Profile data update after login eg: First name, last name, country, language & profile picture | User will be created in system post that. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Registration & Login | Login | Login with email id & password | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 3 | 2 | 0 | 0 | 3 | S
Registration & Login | Login | Forgot / reset password |  |  | This will be handled through firebase auth |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 5 | 4 | 0 | 0 | 5 | S
Registration & Login | Login | Social Media Login (Google, Apple) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 21 | 16 | 0 | 0 | 17 | S
Registration & Login | Auth handle after registration/login |  | • Based on auth state, redirection will happen. On successful authentication, we will fetch user details from BE. • Auth middleware creation in BE | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 4 | S
Splash Screen & App icon | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Questionnaire | View Questionnaire form | View questions with possible options |  |  | These will be fetched from CMS |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 21 | 16 | 3 | 2 | 0 | 0 | 18 | S
Questionnaire | View Questionnaire form | Add answers | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Questionnaire | View Questionnaire form | Edit answers | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Questionnaire | View Questionnaire form | Delete answers | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Questionnaire | Submit form |  | Based on user input, BE will recommend product to users | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 0 | 0 | 3 | S
Home page | Search products |  | Product indexing setup also has to be done. Multilingual search support will be there | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Home page | Filter & Sorting | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 3 | 2 | 5 | 4 | 17 | S
Home page | Multilingual search support | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Home page | Hero Banner + 1 Banner | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home page | Categories | [9 empty] | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home page | Learn about | [9 empty] | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home page | Popular Scans/Recommeded products | [9 empty] | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home page | Switch user | Profile User (Name and picture) | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 |  | 0 | 2 | S
Home page | Switch user | List of users to Switch (Dropdown) |  |  | On changing profile, we have to change user configs through BE. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 |  | 0 | 4 | S
Scan Product | Upload image of product/capture image | Select image from gallery | Approach for this will be same as scanning label using device's camera. Instead of taking photo, we will share the image from gallery for scanning. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Scan Product | Scan product label using app's camera |  | We will check if there is any product exists with the scanned result. If any product exists for the scanned label then we will add this scanned label information under user account. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 21 | 16 | 3 | 2 | 0 | 0 | 18 | S
Scan Product | View result/ result of products | Show matched product details | If there is any match then we will take user to product details view. If there is no successful match then show the error message | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Product Catalogue | Products List | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
Product Catalogue | Search | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Product Catalogue | Filter | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Product Catalogue | Sort | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Product details | Basic details | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 |  | 0 | 6 | S
Product details | Certification tooltip | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 |  | 0 | 4 | S
Product details | Mark as used | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Sponsored product tag, if applicable. | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 |  | 0 | 0.5 | S
Product details | Mark as Favourite | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Share Product via email, whatsapp, facebook, insta etc. | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 3 | 2 |  | 0 | 2.5 | S
Product details | Ratings & Reviews | Average rating & number of reviews | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 |  | 0 | 8 | S
Product details | Ratings & Reviews | Add review | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 |  | 0 | 8 | S
Product details | Ratings & Reviews | List of reviews | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 |  | 0 | 5 | S
Product details | Ratings & Reviews | Like/ dislike review | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Ratings & Reviews | Report Review | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Ratings & Reviews | Recommend | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 |  | 0 | 1 | S
Product details | FAQs | List of FAQs | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 |  | 0 | 3 | S
Product details | Q&A | List of questions & answers | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 3 | 2 |  | 0 | 13 | S
Product details | Q&A | Add question | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 |  | 0 | 3 | S
Product details | Q&A | Add answer | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 |  | 0 | 3 | S
Product details | Q&A | Edit/ delete questions added by you | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 |  | 0 | 4 | S
Product details | Q&A | Edit/ delete answers added by you | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 |  | 0 | 4 | S
Product details | Q&A | Like/ dislike answers | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Q&A | Mark as me too questions | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Q&A | Report answers | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Q&A | Report a question | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 |  | 0 | 1.5 | S
Product details | Similar products | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 |  | 0 | 4 | S
Product details | Compare product | search for products to compare | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 |  | 0 | 11 | S
Product details | Compare product | Comparison view | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 0 | 0 |  | 0 | 16 | S
Product details | Compare product | Draggable list | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 |  | 0 | 4 | S
Product details | Compare product | Remove product from list | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 |  | 0 | 1 | S
Product details | Seller details | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 |  | 0 | 2 | S
Language - English & Arabic |  |  |  |  | Translate content to other language using google translate API |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Dosage Reminder | Search Medicine | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 3 | 2 |  | 0 | 9 | S
Dosage Reminder | Add Medicine | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 |  | 0 | 2 | S
Dosage Reminder | Set Dosage Reminder | Select medicine type | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 |  | 0 | 2 | S
Dosage Reminder | Set Dosage Reminder | Specify dosage frequency | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 0 | 0 |  | 0 | 7 | S
Dosage Reminder | Set Dosage Reminder | Dosage refill reminder | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 |  | 0 | 4 | S
Dosage Reminder | Set Dosage Reminder | Set reminder | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 |  | 0 | 2 | S
Dosage Reminder | Reminders List | Calendar view with list | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 3 | 2 | 0 | 0 | 13 | S
Dosage Reminder | Reminders List | Status of reminder | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Dosage Reminder | Active Medicine | List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 1 | 0 | 0 | 5 | S
Dosage Reminder | Active Medicine | Pause Medication | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 1 | S
Dosage Reminder | Active Medicine | Edit Medication | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 1 | 0 | 0 | 5 | S
Dosage Reminder | Active Medicine | Delete Medication | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 1 | S
My profile | Basic Profile details | View/edit profile details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
My profile | Basic Profile details | Reset password | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | S
My profile | Products Used | Product List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 |  | 0 | 3 | S
My profile | Products Used | Mark / Unmark Favorite | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 |  | 0 | 3 | S
My profile | My favourite | List of products | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
My profile | My favourite | Mark as Favorite / Unfavorite | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 |  | 0 | 3 | S
My profile | Ratings and reviews | List of ratings and reviews | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 2 | 1 | 0 | 0 | 8 | S
My profile | Ratings and reviews | Add /edit my reviews | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 1 | 0 | 0 | 5 | S
My profile | Ratings and reviews | Delete reviews | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
My profile | Scanned Labels | List of previously scanned products | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
My profile | Family Members | List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
My profile | Family Members | Add Family Member | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 3 | 2 | 0 | 0 | 13 | S
My profile | Family Members | Edit Details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
My profile | Family Members | Delete | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
My profile | Notification Settings | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
My profile | Nutralis Support | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 4 | S
UX Process | Brainstorming & Research | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Requirement Gathering | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | User Flow | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Competitive Analysis | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Notification | List | Setup | We will use react native firebase notification | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 16 | 0 | 0 | 16 | S
Notification | List | List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 3 | 2 | 0 | 0 | 13 | S
Style Guide | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Logo & Branding | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Logout | Manual logout | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | S
Prototype | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Chat bot support | Chatsupport functionality with UI | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 55 | 40 | 13 | 11 |  | 0 | 51 | M
Chat bot support | Speech to text conversion | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 8 | 7 |  | 0 | 18 | S
Blogs | Blog List | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 3 | 2 |  | 0 | 13 | S
Blogs | Blog Details | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 3 | 2 |  | 0 | 2 | S
Blogs | Quick Categories | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 |  | 0 | 2 | S

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have