## Web App - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 90.5 | Visual Design Story Points | 123.5 | Frontend Story Points | 213 | Integration Story Points | 108.5 | Backend Story Points | 281 | 602.5 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Non Functional | Boilerplate | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 5 | 4 | 21 | 16 | 36 | M
Non Functional | ERD |  |  |  | db planning, relation mapping & verification with client |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 34 | 24 | 24 | S
Login | Email ID | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Login | OTP | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Login | Login with SSO |  |  |  | will try to reutilize the sso flow of admin end as base layer |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 5 | 4 | 5 | 4 | 8.5 | S
Policies rule Validation checks engine | payment policy rule |  | pre-pay checks & post pay autocharge user for remaining balance cron setup |  | this will include pre payment rule check, post autocharge with specified date, specified amount if selected, autopay attempts fails then admin will sort this out on ground |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 21 | 16 | 17 | S
Policies rule Validation checks engine | cancellation policy rule check + charge the penalty amount as per rule |  | check cancellation restrictions, post cancellation charge penalty % amount as per rule | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 13 | 11 | 12 | S
Policies rule Validation checks engine | minimum room night & multiple room booking rule | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 5 | 4 | 5 | S
Policies rule Validation checks engine | hotel operational & custom text policy rulle |  |  |  | these are only be shown as preview text during booking journey no system rule checks needed |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Lock & release inventory mechanism during cart creation | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 21 | 16 | 22 | S
Hotels List & Booking Flow | Check in and check out date | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Hotels List & Booking Flow | Search ¦ Sort ¦ Filter (Based on Events) | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Hotels List & Booking Flow | View Hotels List | List View | [7 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 3 | 2 | 8 | 7 | 13 | S
Hotels List & Booking Flow | View Hotels List | Map View | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 0 | 0 | 2 | 1 | 12 | S
Hotels List & Booking Flow | View Hotels List | Grid view | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Hotels List & Booking Flow | View Hotel details | Explore Rooms view, about hotel | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 | 8 | 7 | 15 | S
Hotels List & Booking Flow | View Hotel details | Amenities | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Hotels List & Booking Flow | View Hotel details | Distance to venue, Room types, Nightly rates | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Hotels List & Booking Flow | View Hotel details | Hotel Policies | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Hotels List & Booking Flow | View Hotel details | Booking and refund policies | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Hotels List & Booking Flow | Booking Flow | Select the room type + Checkin/checkout dates + count of rooms | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 8 | 7 | 15 | S
Hotels List & Booking Flow | Booking Flow | Preview Summary View | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotels List & Booking Flow | Booking Flow | Summary Page & modify the current booking state |  |  | frontend state management will be done here |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Hotels List & Booking Flow | Booking Flow | Add Guest | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotels List & Booking Flow | Booking Flow | Review Policies | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Hotels List & Booking Flow | Booking Flow | Payment View - Bills and taxes(add to cart type) |  |  | add to cart api, inventory lock/release mechanism api to use here |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 8 | 7 | 13 | S
Hotels List & Booking Flow | Booking Flow | More details (Description) | Collect necessary information about the guest (and any additional guests sharing the room). This includes name, contact information (phone, email), and possibly special requests (like dietary needs for breakfast or accessibility requests). User is logged in as an attendee, some details can be pre-filled from their profile to streamline the process. |  | ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Hotels List & Booking Flow | Booking Flow | Select the Check-in and Check out dates | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 0 | 0 | 0 | 0 | 4 | S
Hotels List & Booking Flow | Bulk Booking | Check in and check out date | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Hotels List & Booking Flow | Bulk Booking | Select room type | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Hotels List & Booking Flow | Bulk Booking | Reservation view | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 | 3 | 2 | 10 | S
Hotels List & Booking Flow | Bulk Booking | Preview Summary View | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Hotels List & Booking Flow | Bulk Booking | Booking Summary Page(add to cart type) |  |  | 1. add to cart api 2. inventory lock/release mechanism api to use |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 8 | 7 | 11 | S
Hotels List & Booking Flow | Bulk Booking | Modify Current Booking State | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotels List & Booking Flow | Bulk Booking | Add guest details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 3 | 2 | 4 | S
Hotels List & Booking Flow | Bulk Booking | Add/Edit number of rooms per day | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Hotels List & Booking Flow | Make a Payment (Stripe) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 13 | 11 | 34 | 24 | 39 | M
Hotels List & Booking Flow | Booking confirmation |  |  |  | save booking with all transactional details |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 13 | 11 | 14 | S
Hotels List & Booking Flow | Trigger Booking Email confirmation |  | also setup other system booking emails | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 13 | 11 | 15 | S
My Bookings | Bookings List ( Present Bookings / Past Bookings / Cancelled) |  | Tab is not needed as per the design. | [6 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
My Bookings | View Booking details | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
My Bookings | Modify Booking |  | * | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
My Bookings | Confirmation screen on Modification / Cancellation |  | * | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
My Bookings | Cancel Booking + Additional Remarks |  | * | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
My Bookings | Show cancellation / modification charges | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
My Bookings | Make a payment (For modification) + Booking confirmation | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 13 | 11 | 8 | 7 | 22 | S
My Bookings | Trigger email to Event Admin incase of cancellation | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 5 | 4 | 8 | S
My Bookings | Download Invoice |  | iInclude invoice setup with branding also here |  | all booking transactional invoices considering here, invoice capture from stripe |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 8 | 7 | 9 | S
My Bookings | Search ¦ Sort ¦ Filter | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Notifications | Booking confirmation Email |  | Email to the user immediately after booking with all details. Optionally, send a summary to relevant admins or hotel contacts if needed (for example, the hotel could get a daily report of new reservations). | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 3 | 2 | 2 | 1 | 2 | 1 | 13 | 11 | 13 | S
Notifications | Post-Modification Notices: |  | If a booking is changed or canceled, send an updated confirmation or a cancellation notice to the user. If admin approval was needed for a change, notify the user that their request has been processed or require further action. | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 3 | 2 | 3 | 2 | 1 | 0.5 | 8 | 7 | 9.5 | S
Contact Support (Contact info) |  |  | Contact mail id is mentioned | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Profile |  |  | We just have logout under Profile |  | view and edit is considered |  |  |  |  | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Logout | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 1 | S
User journey Analytics Integration(Optional) |  |  |  |  | basic Firebase basic event based analytics |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 24 | 0 | 0 | 24 | S
Tab Responsive | [9 empty] | Simple | Must Have |  |  |  |  | 13 | 11 | 34 | 24 | 21 | 16 | 0 | 0 | 0 | 0 | 16 | S
Mobile Responsive | [9 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 55 | 40 | 21 | 16 | 0 | 0 | 0 | 0 | 16 | S
Join Waitlist for Sold-out rooms | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
UX Process | Competitive Analysis | [8 empty] | Simple | Must Have |  |  |  |  | 21 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | User Flow | [8 empty] | Simple | Must Have |  |  |  |  | 21 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Brainstorming & Research | [8 empty] | Simple | Must Have |  |  |  |  | 13 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Requirement Gathering | [8 empty] | Simple | Must Have |  |  |  |  | 13 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Style Guide | [9 empty] | Simple | Must Have | [5 empty] | 0 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Prototype | [9 empty] | Simple | Must Have | [5 empty] | 0 | 34 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S

## Admin Panel - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 73 | Visual Design Story Points | 173 | Frontend Story Points | 562 | Integration Story Points | 232 | Backend Story Points | 673.5 | 1467.5 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login | Via Email and Password | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Login | Forgot Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Login | Send verification email | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | S
Login | Reset Password | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 2 | S
Login | Via Email + OTP |  |  |  | assuming system based otp generation here with sending out emais |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 8 | 7 | 9.5 | S
Login | Resend OTP | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | S
Login | Via SSO |  |  |  | User clicks "SSO Login" on Next.js app Next.js redirects user to existing system's SSO endpoint User authenticates on existing system (or already logged in) Existing system generates signed token Existing system redirects user back to Next.js with token Next.js sends token to Nest.js API for validation Nest.js validates token signature and extracts user info & shadow user to db if it's a new user, Nest.js creates local session and returns session token Next.js stores session token and grants user access User is now logged into new system with SSO session Summary: User → Next.js → Existing System → Authentication → Token → Next.js → Nest.js → Validation → Session → Access Granted, for now basic sso flow assumed here as above defined, efforts will be adjusted post flow confirmation |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 13 | 11 | 21 | 16 | 29 | S
Event Management | Add New Event | Add New Event CTA Screen | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Event Management | Add New Event | Search Event | Fetch events list already present in the XCD system |  | assuming we will be calling xcd api for searching & fetching event details form our BE with xcd valid usr token as needed |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Event Management | Add New Event | Select Event, showing popups | Fetch specific event details from XCD |  | assuming we will be calling fetch events details from xcd using user xcd token as per need in our BE |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Event Management | Add New Event | Add Event Details |  |  | storing events details in our db side with event logo on s3 with additional details(S3 provider setup efforts considered here), google maps integration (search api, coordinates to location map) |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 13 | 11 | 22 | S
Event Management | Add New Event | Add primary support contact & Finish Event Setup |  |  | store events details in BE With all information |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Event Management | My Events View Page |  |  |  | fetch events list created in our BE with search & sort capability option |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Event Management | View Event overview | Total revenue | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | S
Event Management | View Event overview | Revenue this month | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | S
Event Management | View Event overview | Hotels added | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | S
Event Management | View Event overview | Bookings done | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | S
Event Management | View Event overview | show basic events details |  |  | fetch particular event detail from an api which is saved in our db side |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Event Management | Support Contact |  |  |  | Is this a static data or pulled dynamically from db as per event wise ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 5 | 4 | 6 | S
Event Management | Add category | Add general/ multiple category | Categorise by Group/Registration |  | fetch categories by group & registration api from xcd user token will call from our BE, add categories add api for adding category in our Backend |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 3 | 2 | 13 | 11 | 24 | S
Event Management | Add category | View & Manage Category |  |  | view & update category api will use here |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 8 | 7 | 16 | S
Event Management | Add category | Delete Category | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 3 | 2 | 3.5 | S
Event Management | Add category | View, adjust, preview Category policy | Inherited from event policy, also here only we are creating policy crud for category, event, hotel, room, sub-block as base setup, will re-utilize at other places |  | inherit policy from event as api call and then adjust category policy as override api, category policy crud will use thru out for other as per need for hotel, room, sub-block policy, back reflections won't work here suppose if someone change event policy then it won't change policy for its associated hotels, only first time inherit will work untill not setup |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 8 | 7 | 21 | 16 | 39 | M
Event Management | Edit Event | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Event Management | Set up Event Policy | Add policy | takes us to policy module |  | inherit from policy management api |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Event Management | Set up Event Policy | Edit Policy |  |  | add event policy api with inherited value or override value |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Event Management | Set up Event Policy | Preview Policy | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Event Management | Set up Event Policy | Audit logs |  |  | considering paginated tabular list view with search filter option, drop down api needed also for team member search list |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 | 13 | 11 | 19 | S
Event Management | Active/Inactive Event | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 3 | 2 | 4.5 | S
Event Management | Delete Event | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 3 | 2 | 4.5 | S
Event Management | Enable/Disable status digest | Add/edit/delete recipients |  |  | In BE we have to save the recipients and enable/disable the schedule as per toggle so 2 api's needed |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 | 8 | 7 | 15 | S
Event Management | Enable/Disable status digest | Set frequency + Send Digest Summary Email |  |  | frequency set api needed |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 8 | 7 | 12 | S
Policy Management | Block Level Policies (Add and Modify) |  | When editing, the admin is presented with appropriate input fields (e.g., date pickers for cancellation deadlines, numeric fields for deposit amounts, toggles for dynamic pricing options). Upon saving, the system validates the inputs (ensuring logical deadlines and amounts) and immediately updates the active policy. A “Reset to Default” option is available to revert any overridden policy back to its inherited value. | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Policy Management | Hotel Level Policies (Add and Modify) | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Policy Management | Room level policies (Add and Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Policy Management | Cancellation Policy (Add/Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Policy Management | Payment Policy (Add/Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Policy Management | minimum room night Policy (Add/Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Policy Management | multi-room booking limit policy Policy (Add/Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Policy Management | hotel operational payment Policy (Add/Modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Policy Management | Custom Text Policy(Add/modify) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Policy Management | Audit logs | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | Add Hotel | Search |  |  | have to check for public api resources which can be fit in here |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 8 | 7 | 10 | S
Hotel Management | Add Hotel | Create hotel manually |  |  | save hotel in our db either from global api details or manual entry |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 5 | 4 | 6 | S
Hotel Management | Add Hotel | Hotel Details | Hotel address, location on map, hotel description, hotel rating |  | fetch from global hotel api or add manually and save those details in db |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 5 | 4 | 3 | 2 | 10 | S
Hotel Management | Add Hotel | Hotel Address | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 2 | 1 | 3 | S
Hotel Management | Add Hotel | upload images (media) |  |  | s3 upload and store url db end |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 2 | 1 | 5 | 4 | 12 | S
Hotel Management | Add Hotel | Amenities(Search,select,add custom) | Add custom amenity CTA is present in designs |  | get amenity list, search, add & store new custom amenities.By default from db dataset will be showing set of amenities, select amenities from available list, Sp prepare amenities dataset |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 13 | 11 | 16 | S
Hotel Management | Add Hotel | Add Tag | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 5 | 4 | 8 | S
Hotel Management | Add Hotel | Preview hotel | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 5 | 4 | 8 | S
Hotel Management | Add Hotel | save hotel |  |  | moved hotel from draft to active state |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 3 | S
Hotel Management | Add Hotel | Active/inactive hotel | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Hotel Management | Hotel List | Search | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Hotel Management | Hotel List | Sort | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0.5 | 2.5 | S
Hotel Management | Hotel List | Filter | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0.5 | 2.5 | S
Hotel Management | Hotel List | List | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | View Hotel Details | (Overview) tab | Overview, sub-block, rooms, inventory and pricing, hotel policies |  | api for total revenue, revenue by month, booking done count, rooms available, inventory status, Single api for all above data fetch |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 3 | 2 | 8 | 7 | 16 | S
Hotel Management | View Hotel Details | Sub-block tab view |  |  | check Sub block List for efforts |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Hotel Management | View Hotel Details | room type tab view | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Hotel Management | View Hotel Details | Inventory & Pricing Tab |  |  | no exact defined room type soo generic room type inventory considering here |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 5 | 4 | 8 | 7 | 27 | S
Hotel Management | View Hotel Details | hotel policies tab view |  |  | inherit from event and update as per need so 2 api's |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | View Hotel Details | Hotel policy Audit logs | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Hotel Management | View Hotel Details | View Hotel Rooms List | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | View Hotel Details | View Room details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Hotel Management | View Hotel Details | Edit Room details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | View Hotel Details | Delete room | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Hotel Management | View Hotel Details | Allow bulk updates of rooms | If room rates or attributes need to change for many rooms, the system will allow batch editing. For instance, an admin could select all “Standard Queen” room types and update the price or amenity in one action. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Hotel Management | Edit Hotel Details | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Hotel Management | Add room type | Search room type | seeder room type list fetch | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | S
Hotel Management | Add room type | Create manually | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 5 | 4 | 6 | S
Hotel Management | Add room type | Fill details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Hotel Management | Add room type | Upload images | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 3 | 2 | 3.5 | S
Hotel Management | Add room type | Add amenities | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Hotel Management | Add room type | Set room inventory and pricing |  |  | will extend base room inventory ui & BE for room type also |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Hotel Management | Add room type | Set room policies |  |  | inherit hotel policy and override as per need |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Hotel Management | Edit room type | edit room details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 5 | 4 | 8.5 | S
Hotel Management | Edit room type | Review Policy |  |  | where in wireframe ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 3 | 2 | 4.5 | S
Hotel Management | Edit room type | Audit logs |  |  | where in wireframe ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Hotel Management | Delete room type | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Hotel Management | Enable / Disable Hotel |  | Active/Inactive Hotel | [6 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | S
Hotel Management | Delete Hotel | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | S
Hotel Management | Add Room | Set Occupancy Limits | Define the maximum number of guests per room (e.g., 2 adults, or 2 adults + 2 children). This will be used to control bookings (the system won’t allow more guests than the limit). | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 8 | 7 | 8 | 7 | 16 | S
Hotel Management | Add Room | Set Bed type | Options like King, Queen, Double Twin, etc., selectable per room type. If a room type offers multiple configurations (e.g., “Two Queens or One King”), the system can list variants or note it in the description. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Set Smoking Preference | Mark rooms or room types as Non-smoking or Smoking allowed. Many modern hotels are entirely non-smoking, but the setting is tracked especially if some rooms in the block permit smoking. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Accessibility Features : Mark which is applicable | Flags for ADA/accessibility features, such as wheelchair-accessible rooms, roll-in showers, or grab bars. Users with needs can filter or request these, and admins can ensure a certain inventory of accessible rooms is set aside. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Hotel Management | Add Room | Set if its available for all / VIP customers [Sub-blocks] | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Set discounts | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Pricing per Night :: Static (Dynamic Price) | If enabled, the price might be modified by the dynamic rules (from Policy Management). The room config can include a toggle “Allow dynamic pricing adjustments” so that the pricing engine knows which rooms to adjust. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Pricing per Night :: Static (Fixed Price) | A fixed rate (possibly different for weekdays vs weekends, or pre-defined seasonal rates). | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Amenities : Display the list and mark applicable | List standard amenities (Wi-Fi, breakfast included, parking, minibar, etc.). These can be predefined tags or free-text notes. Amenities will appear in the user booking interface as icons or a list, and can be used as filters (e.g., “show only rooms with free breakfast”). | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Special conditions :: Set discounts for VIP customers only | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Hotel Management | Add Room | Add Cancellation policies | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Set the slabs for cancellation (Eg : Within 7 days - 100% refund, Within 3 days - 40% refund, etc) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Set limit - 1 room per user or add manually the count | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Additional Details (View Description) | Optionally include room size (sq. ft.), floor level, or photos and descriptions to help users understand what they are booking. (While not explicitly requested, including images and detailed descriptions can enhance user choice.) | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Hotel Management | Add Room | Specify the number of rooms (Bulk creation) | The admin module will support bulk creation of room inventory. For example, after defining a room type (e.g., “Deluxe King Room”), an admin can specify the number of such rooms allocated to the event block (e.g., 50 rooms) and the system will create an inventory count of 50 available rooms of that type. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 8 | 7 | 15 | S
Sub block management | Add Sub block | Enter name | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Sub block management | Add Sub block | Select category sub block is applicable to | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Sub block management | Add Sub block | Create sub block | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 2 | 1 | 5 | 4 | 5.5 | S
Sub block management | Add Sub block | Assign rooms | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 5 | 4 | 6.5 | S
Sub block management | Add Sub block | Set pricing and inventory |  |  | sub-block vs main-block difference ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Sub block management | Add Sub block | Sub block policies | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Sub block management | Add Sub block | Basic Form | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 13 | 11 | 8 | 7 | 13 | 11 | 29 | S
Sub block management | Sub block List | Search | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Sub block management | Sub block List | Sort | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0.5 | 2.5 | S
Sub block management | Sub block List | Filter | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0.5 | 2.5 | S
Sub block management | Sub block List | List | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Sub block management | View Sub bock | Sub-block overview | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 8 | 7 | 11 | S
Sub block management | View Sub bock | View pricing and inventory | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 5 | 4 | 6.5 | S
Sub block management | View Sub bock | View Sub block policies |  |  | inherit and override api |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 5 | 4 | 5.5 | S
Sub block management | View Sub bock | View the rooms list within sub blocks | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Sub block management | View Sub bock | View Room details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Sub block management | View Sub bock | Unassign or Reassign room to another sub block | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Sub block management | Edit Sub block | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Sub block management | Delete Sub block | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | S
Sub block management | Enable / Disable Sub block | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1.5 | S
Customer Management | XCD Admin Login to xcd customer portal with sso/email link | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 8 | 7 | 13 | S
Customer Management | Add customer | Select customer |  |  | from where we will fetch the customers ?, Is they are event organisers ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 5 | 4 | 6.5 | S
Customer Management | Add customer | Fill details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 3 | 2 | 4.5 | S
Customer Management | Add customer | Send Invite |  |  | BE not clear how invite will work |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 5 | 4 | 5 | S
Customer Management | Add customer | Save Customer |  |  | we will be saving customer in our db right ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 4 | S
Customer Management | Customer List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 3 | 2 | 5 | S
Customer Management | Customer List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Customer Management | Customer List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Customer Management | Customer List | List | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Customer Management | Customer List | KPIs | All customers, Events, Active customers, Inactive customer | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 5 | 4 | 5 | S
Customer Management | View Customer Details | Customer Details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Customer Management | View Customer Details | View Customer Bookings List | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Customer Management | View Customer Details | View Booking Details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 2 | S
Customer Management | View Customer Details | Download invoice | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Customer Management | View Customer Details | Download Customer Bookings List | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Customer Management | Edit Customer Details (Contact Information) |  | All details like name, email address, phone no | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
Customer Management | Enable/Disable Customer | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | S
Customer Management | Delete Customer | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Customer Management | Manage Customer |  | Switches the role from XCD admin to XCD customer |  | admin will be logged in into event portal with internal verification |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 3 | 2 | 6.5 | S
Customer Management | Download Customer List (Single or Multiple) |  |  |  | Considered as a PDF in tabular format |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Dashboard | Total room nights reserved | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Dashboard | Overall pickup rate | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 3 | 2 | 3 | 2 | 4.5 | S
Dashboard | % of attendees made reservation | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Dashboard | Event coverage | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Dashboard | Total committed revenue | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 2 | 1 | 1.5 | S
Dashboard | Average room nights/reservation | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Dashboard | Total cancellations | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 2 | 1 | 1.5 | S
Dashboard | Hotel comparison | Individual hotel metrics |  |  | see hotel regency design page |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 13 | 11 | 16 | S
Dashboard | Hotel comparison | All Hotel comparison List View | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 8 | 7 | 11.5 | S
Dashboard | Widget for hotel performance | Booking pace | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 5 | 4 | 8.5 | S
Dashboard | Widget for hotel performance | Booking velocity | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 5 | 4 | 8.5 | S
Dashboard | Widget for hotel performance | Daily pickup rate | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 5 | 4 | 6.5 | S
Dashboard | Widget for hotel performance | Performance analytics | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 1 | 0.5 | 5 | 4 | 8.5 | S
Dashboard | Sort and filter for hotel performance |  |  |  | hotel list api as dropdown for filter and one api for providing filtered based set of results for Hotel comparison view |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 8 | 7 | 11 | S
Dashboard | Alerts | Alerts to capturing in BE System |  |  | what sort of alerts to capture to show later on as alert list ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | S
Dashboard | Alerts | Read/unread indicator | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Dashboard | Alerts | Mark all as read | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | S
Dashboard | Alerts | alert list | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Dashboard | KPIS (Statistics) | Total bookings made and total cancellations (perhaps with a ratio or trend indicator). | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Dashboard | KPIS (Statistics) | Current pick-up/occupancy rate per hotel or overall (e.g., “120 of 200 rooms booked, 60% occupancy”). | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Dashboard | KPIS (Statistics) | Revenue collected to date and any outstanding payments (for deposits or balances not yet charged). | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Dashboard | KPIS (Statistics) | Upcoming important dates and tasks (e.g., “Cancellation deadline in 5 days for Event X” or “Room release for Hotel Y tomorrow”). | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Dashboard | Visulaizations | A line or bar chart of bookings over time (booking pace) leading up to the event. | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Dashboard | Visulaizations | A pie chart or bar breakdown of room types booked (to see which room types are most popular). | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1.5 | S
Dashboard | Visulaizations | Progress bars for each hotel’s block showing percentage booked vs remaining, and another for minimum pickup vs achieved. | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1.5 | S
Dashboard | Visulaizations | Interactive Dashboard | Clicking on a metric or chart segment can drill down to more details. For example, clicking on “Cancellations: 25” could open a list of those canceled reservations and their details. | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 8 | 7 | 3 | 2 | 13 | 11 | 20 | S
Dashboard | Analytics | Cancellation Rate | Calculate the percentage of bookings that were canceled and when they occurred. For instance, if many cancellations occur right before the penalty kicks in, that indicates users are very aware of the policy timing. | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | 7 | 13 | S
Dashboard | Analytics | Refund vs. Retained Revenue | Measure how much money was refunded due to cancellations vs. retained. A high refund amount might indicate a too-lenient policy (or external factors causing cancellations), whereas a low cancellation/refund rate might mean policies are strict but effective. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Dashboard | Analytics | Early-Bird vs. Regular Bookings | If dynamic pricing/discounts were used, analyze how many bookings happened during the discounted period versus afterward. This shows if the early-bird incentive successfully drove early reservations. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Dashboard | Analytics | Override Frequency | Track how often admins had to override or adjust policies (e.g., manual fee waivers). Frequent overrides might highlight that a policy is too strict or causing user dissatisfaction, which is valuable feedback. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Dashboard | Additional | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Dashboard | Filters | Specific Event | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Notifications Template Management/ Email templates | Notification Templates List | List | [7 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Notifications Template Management/ Email templates | Notification Templates List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Notifications Template Management/ Email templates | Notification Templates List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 2 | 1 | 1 | 0.5 | 2 | S
Notifications Template Management/ Email templates | Notification Templates List | Filter | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 2 | 1 | 4 | S
Notifications Template Management/ Email templates | Manage template elements | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Notifications Template Management/ Email templates | View Template | open in preview & edit mode | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 7 | S
Notifications Template Management/ Email templates | View Template | Reset to default |  |  | ? |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Notifications Template Management/ Email templates | View Template | send test email | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 5 | 4 | 5 | S
Notifications Template Management/ Email templates | Save template |  |  |  | only edit exisitng template, not adding new template |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 3 | 2 | 3 | S
Notifications Template Management/ Email templates | Delete | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 3 | 2 | 3 | S
Notifications Template Management/ Email templates | Create New Notification | Add Notification Details + Image (Optional) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Notifications Template Management/ Email templates | Create New Notification | Rich text Editor | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 5 | 4 | 8 | 7 | 22 | S
Notifications Template Management/ Email templates | Edit Template | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Notifications Template Management/ Email templates | Enable / Disable | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Profile | View Profile | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Profile | Edit Profile | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 2 | S
Bookings Management | Bookings List (All including the payment failures as well) | Search | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Bookings Management | Bookings List (All including the payment failures as well) | Sort | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Bookings Management | Bookings List (All including the payment failures as well) | Filter (By event, by hotel, by status,room,category) | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 5 | 4 | 6 | S
Bookings Management | Bookings List (All including the payment failures as well) | List - view reservation, groups, cancellations |  |  | 3 tabs data fetch as api with types |  |  |  |  | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 21 | 16 | 24 | S
Bookings Management | Allow to do a Booking Reservation | Same workflow as user | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 2 | 1 | 5 | 4 | 9 | S
Bookings Management | View Booking Details | View details - booking, cancellation | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 8 | 7 | 13 | S
Bookings Management | View Booking Details | Modify single booking resevation |  |  | BE api for refund/paid/due type handling |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 13 | 11 | 17 | S
Bookings Management | View Booking Details | Modify group booking reservation | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 13 | 11 | 16 | S
Bookings Management | View Booking Details | Ability to cancel a booking (based on customer request) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Bookings Management | View Booking Details | View modification charges | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
Bookings Management | View Booking Details | Payment gateway |  |  | charging payment from invoice links to users and tracking those on db level from webhook |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 21 | 16 | 17 | S
Bookings Management | Download Invoice | [8 empty] | Simple | Could Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 5 | 4 | 6 | S
Bookings Management | Audit Logs | List of modifications with Admin name, date and timestamp | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 8 | 7 | 13 | S
Bookings Management | Send Email confirmation | Add mail id | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 0 | 0 | 1.5 | S
Bookings Management | Send Email confirmation | Send | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 1 | 0.5 | 0 | 0 | 3 | 2 | 2.5 | S
Bookings Management | Multi-select bookings | Allow to Download CSV report | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 2 | 5 | S
Bookings Management | Multi-select bookings | Allow Cancellations | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Bookings Management | Multi-select bookings | Allow Policy Updates | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Bookings Management | Multi-select bookings | Allow to undo actions | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Logout | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 1 | S
Tab Responsive | [9 empty] | Simple | Must Have |  |  |  |  | 8 | 7 | 55 | 40 | 21 | 16 | 0 | 0 | 0 | 0 | 16 | S
Mobile Responsive | [9 empty] | Simple | Must Have |  |  |  |  | 13 | 11 | 89 | 60 | 34 | 24 | 0 | 0 | 0 | 0 | 24 | S
Dynamic Pricing Adjustments | Notifications (Email Templates) | Notify admin when all the rooms are almost booked in hotel | For events like nearing cancellation deadlines or failed payment charges, send alerts to administrators. For instance, if an automatic charge for a balance payment fails, flag that reservation and notify admins to follow up with the guest. | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 2 | 1 | 5 | 4 | 0 | 0 | 8 | 7 | 11 | S
Dynamic Pricing Adjustments | Notifications (Email Templates) | Booking confirmation | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 2 | 1 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Dynamic Pricing Adjustments | Notifications (Email Templates) | Booking Cancellation | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Internal Alerts for Admins |  |  | For events like nearing cancellation deadlines or failed payment charges, send alerts to administrators. For instance, if an automatic charge for a balance payment fails, flag that reservation and notify admins to follow up with the guest. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Schedule Email Alerts | Select Hotel | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 5 | 4 | 21 | 16 | 22 | S
Schedule Email Alerts | Select Frequency | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | S
Schedule Email Alerts | Select Start and End date | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | S
Schedule Email Alerts | Daily rooming list update | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 0 | 0 | 0 | 0 | 4 | S
Prototype | [9 empty] | Simple | Must Have |  |  |  |  | 8 | 7 | 34 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have