## Admin Panel - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 26 | Visual Design Story Points | 33.5 | Frontend Story Points | 321.5 | Integration Story Points | 194.5 | Backend Story Points | 259.5 | 775.5 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Login | Google Auth (Sign in) | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Login | Via Email and Password | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Login | Forgot Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Login | Send verification email | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | S
Login | Reset Password | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 2 | S
Backend Reminders + Email Notifications | Contact us emails |  |  |  |  | what is this? |  |  |  |  | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 5 | 4 | 13 | S
Backend Reminders + Email Notifications | New Listing Requests |  |  |  | this will come up in notifications | [5 empty] | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Backend Reminders + Email Notifications | Chat message |  |  |  |  | do we need this? |  |  |  |  | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Customer Management | Customer List | List | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 2 | 1 | 13 | 11 | 5 | 4 | 5 | 4 | 19 | S
Customer Management | Customer List | Filter | Filters for clients, dealers, active, suspended, etc. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 2 | 1 | 5 | S
Customer Management | Customer List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 2 | 1 | 5 | S
Customer Management | Customer List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 2 | 1 | 5 | S
Customer Management | View Customer Details | Customer Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 3 | 2 | 13 | S
Customer Management | View Customer Details | Edit customer details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
Customer Management | View Customer Details | Offers and bids made by Customer with Statistics | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 5 | 4 | 5 | 4 | 3 | 2 | 10 | S
Customer Management | View Customer Details | View the invoices uploaded |  |  |  | do you mean receipt? |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 2 | 1 | 9 | S
Customer Management | View Customer Details | Download Customer report as CSV | [7 empty] | Simple | Could Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 2 | 1 | 7 | S
Customer Management | Listings approval with customer/dealer details | Search ¦ Sort ¦ Filter | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Customer Management | Listings approval with customer/dealer details | List of approvals pending ¦ Published | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Customer Management | Listings approval with customer/dealer details | View Listing details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Customer Management | Listings approval with customer/dealer details | Approve (Able to modify listing details) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1.5 | S
Customer Management | Listings approval with customer/dealer details | Send back for more info | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Customer Management | Listings approval with customer/dealer details | If rejected, add a comment | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 2 | S
Customer Management | Listings approval with customer/dealer details | Notified to seller | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 1 | 0.5 | 2 | 1 | 1.5 | S
Customer Management | Suspend / Un-suspend Customer |  |  |  |  | do we need this? |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Customer Management | Active or Deactivate customer account | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Customer Management | Download Customer List (Single or Multiple) |  |  |  | Considered as a PDF in tabular format |  |  |  |  | Simple | Could Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 5 | 4 | 3 | 2 | 8 | S
Listing Moderation | Listings List | List (Sale ¦ Auction ¦ Reverse Auction) |  |  | assuming, UI will be in tabular form here, we might have different view list UI |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 34 | 24 | 8 | 7 | 3 | 2 | 33 | M
Listing Moderation | Listings List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Listing Moderation | Listings List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Listing Moderation | Listings List | Filter | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Listing Moderation | Add new Listing | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Listing Moderation | View Listing Details | View Listing Details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Listing Moderation | View Listing Details | Edit Listing details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Listing Moderation | View Listing Details | Approve Listing | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Listing Moderation | View Listing Details | Reject Listing + Comment |  |  | Format considered - PDF |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Listing Moderation | View Listing Details | Send back to Seller to Modify few details | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Listing Moderation | View Listing Details | View offers on the listing | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 8 | 7 | 8 | 7 | 25 | S
Listing Moderation | View Listing Details | Hide / Unhide Listing | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 2 | 1 | 4 | S
Listing Moderation | View Listing Details | Upload Signed documents | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 8 | 7 | 15 | S
Listing Moderation | View Listing Details | Upload Invoice against the paid offer | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Listing Moderation | View Listing Details | Update the listing status | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Listing Moderation | View Listing Details | Update bank account details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 3 | 2 | 13 | S
Listing Moderation | Export List |  |  |  |  | do we need it? |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 3 | 2 | 8 | S
Listing Moderation | Add ons | View all the attendee details |  |  |  | attending inspections or auctions? |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Listing Moderation | Add ons | Ability to pause/resume the auction | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Listing Moderation | Add ons | Attendees must be triggered email on pause and resume | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 3 | 2 | 8 | 7 | 10 | S
Listing Moderation | Buyer Info on Admin Panel | Viewing buyer actions (requests, feedback, inspections) | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 |  | 0 |  | 0 | 21 | 16 | 16 | S
Listing Moderation | Buyer Info on Admin Panel | Tracking follow-ups. | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 |  | 0 |  | 0 | 5 | 4 | 4 | S
Listing Moderation | Buyer Info on Admin Panel | Generating and emailing reports automatically. | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 | 21 | 16 | 16 | S
Listing Moderation | Set Campaign type : Vendor run / Unreserved run | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Listing Moderation | Listing Activity |  | All the offers and bids should be displayed in the respective listing. | [6 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Transactions Management | Transaction List | List (Tabs - All transactions, Needs review for refunds) | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Transactions Management | Transaction List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Transactions Management | Transaction List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Transactions Management | Transaction List | Filter | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Transactions Management | View Transaction Details | View Service Details | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Transactions Management | View Transaction Details | View Invoice | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Transactions Management | View Transaction Details | Refund (Specify amount) + Reason | When early returns happen, the backend flags an “Early Return –refund $X pending” for admin. Admin can review the booking details and click to approve or adjust the refund. | [6 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 21 | 16 | 20 | S
Transactions Management | View Transaction Details | Download Invoice |  |  | Format considered - PDF |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 1 | 0.5 | 2 | 1 | 2.5 | S
Transactions Management | Export List | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 8 | 7 | 13 | S
Content Management (Static) | Manage T&Cs | [9 empty] | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 8 | 7 | 0 | 0 | 18 | S
Content Management (Static) | Manage FAQs | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Content Management (Static) | Manage Legals | [9 empty] | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Content Management (Static) | Manage Help center | [8 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Content Management (Static) | Manage Privacy Policy | [9 empty] | Should Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Content Management (Static) | Manage About Us | [9 empty] | Should Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Abiility to change the phone number for Admin | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Enquires Management | Properties List | List | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Enquires Management | Properties List | Search | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Enquires Management | Properties List | Sort | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Enquires Management | Properties List | Filter | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Enquires Management | Enquires List within Properties | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 |  | 0 |  | 0 |  | 0 | 0 | S
Enquires Management | Conversation threads | Buyer / Seller Queries | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 21 | 16 | 5 | 4 | 8 | 7 | 27 | S
Enquires Management | Conversation threads | Respond in Conversation | [7 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 13 | 11 | 5 | 4 | 8 | 7 | 22 | S
In App Notifications | New listing pusblished | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 |  | 0 |  | 0 |  | 0 | 0 | S
In App Notifications | New Support Ticket Raised | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Logout | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 3 | 2 | 4 | S
Prototype | [5 empty] | what is this? |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project Setup | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 8 | 7 | 0 | 0 | 18 | S
RBAC |  |  |  |  | this might not be required with Auth0, this will be moved to admin portal |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 8 | 7 | 21 | 16 | 34 | M

## Vendor and Buyer - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 149 | Visual Design Story Points | 97 | Frontend Story Points | 1073 | Integration Story Points | 689 | Backend Story Points | 992 | 2754 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Landing Page (Web Responsiveness) | Hero Section | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Landing Page (Web Responsiveness) | About Unreserved | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 13 | 11 | 5 | 4 | 0 | 0 | 15 | S
Landing Page (Web Responsiveness) | Types of Sale (Private - Auctions) | [8 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
Landing Page (Web Responsiveness) | Models (Vendor Managed and Unreserved) | [8 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 3 | 2 | 13 | 11 | 5 | 4 | 0 | 0 | 15 | S
Landing Page (Web Responsiveness) | Download our App | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Landing Page (Web Responsiveness) | Create A listing request & send an email | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 55 | 40 | 8 | 7 | 34 | 24 | 71 | M
Landing Page (Mobile Responsiveness) | Hero Section | [8 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Landing Page (Mobile Responsiveness) | About Unreserved | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 5 | 4 | 0 | 0 | 15 | S
Landing Page (Mobile Responsiveness) | Types of Sale (Private - Auctions) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
Landing Page (Mobile Responsiveness) | Models (Vendor Managed and Unreserved) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 5 | 4 | 0 | 0 | 15 | S
Landing Page (Mobile Responsiveness) | Download our App | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Sign up | Social Login | Google | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 5 | 4 | 10 | S
Sign up | Social Login | Apple | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
Sign up | Social Login | Facebook | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 8 | 7 | 11 | S
Sign up | Email and Password |  |  |  | Auth0 will be used |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Sign up | Onboarding | Select the role (Buyer / Seller) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 1 | 0.5 | 6.5 | S
Sign up | Onboarding | Tell us about you | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 1 | 0.5 | 6.5 | S
Sign up | Onboarding | Property Preferences | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 1 | 0.5 | 6.5 | S
Sign up | Onboarding | City Preferences | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 1 | 0.5 | 6.5 | S
Sign up | Onboarding | Budget Preferences | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 1 | 0.5 | 6.5 | S
Login | Email/Username + Password |  |  |  | we will reuse the UI from sign up, Auth0 will be used |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Login | Forgot Password | Provide email ID | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 5 | 4 | 3 | 2 | 13 | S
Login | Forgot Password | Send password reset email (15 min expiration) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Login | Forgot Password | Email clicks on password reset link | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Login | Forgot Password | New Password + Confirm Password | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Login | Forgot Password | Re-attempt login |  |  | re attempt login will be a login screen only, hence considering that |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
Login | Social Media Login :: Google, Apple, Facebook |  |  |  | we will reuse the UI from sign up, Auth0 will be used |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 8 | 7 | 13 | S
Home Page | Find a Property | Search a property |  |  | Estimating only considering text based search. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 5 | 4 | 13 | 11 | 22 | S
Home Page | Find a Property | Filters : Type ¦ Budget ¦ Location ¦ Radius | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Home Page | Find a Property | List of Properties | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 34 | 24 | 21 | 16 | 21 | 16 | 56 | M
Home Page | Find a Property | View property details |  |  | we will have to considering a lot of cases and screens depending on the sale type and status of docs. |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 55 | 40 | 34 | 24 | 34 | 24 | 88 | L
Home Page | Find a Property | Shortlist a property |  |  | assuming this is the wishlist button |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Home Page | Find a Property | View seller profile |  |  | we will show masked details with the property details page, On require or call action it will just send a mail notification. |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 8 | 7 | 8 | 7 | 21 | S
Home Page | Make an offer | Display the list of shortlisted properties for sale |  |  | we will reuse the components from above listing module |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Home Page | Make an offer | CTA :: Request for inspection |  |  | assuming this is where we take ke slot details., estimating fr the 2 screens present in wireframes |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 21 | 16 | 8 | 7 | 8 | 7 | 30 | S
Home Page | Make an offer | CTA :: Make an offer |  |  | Assuming this is where we give numbers / offers., estimating it according to the multiple screens in the wireframe |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 21 | 16 | 13 | 11 | 21 | 16 | 43 | M
Home Page | Make an offer | Submit offer: Details to be added by Buyer and then Submit | Offer price, deposit amount, settlement terms, expiry date, special conditions and T&Cs. |  |  | what is to be done on contact us? |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 8 | 7 | 13 | 11 | 29 | S
Home Page | Make an offer | Vendor accepts the offer or Proposes counter offer |  |  | Placement for this module will be in listing section and notifications. |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 21 | 16 | 13 | 11 | 21 | 16 | 43 | M
Home Page | Make an offer | Counter offer :: Accept or Decline |  |  | considering the flow from wireframes, there are 4 screens as of now. we will also consider signing for counter offer process as well. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 34 | 24 | 21 | 16 | 13 | 11 | 51 | M
Home Page | Make an offer | Accepted :: Offer summary + Legal agreement with Sign | Third party integration for digital signature. |  | Stripe identity integration will be added separately, considering for both seller and buyer, some components can be reused from above |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 34 | 24 | 13 | 11 | 13 | 11 | 46 | M
Home Page | Make an offer | Proceed to Payment :: Bank Account details | Payment via Stripe |  | this will just show payment status on our end. and give upload receipt options. and at vendor's side it will show payment acknowledgement |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 8 | 7 | 8 | 7 | 25 | S
Home Page | Make an offer | Upload Payment Receipts |  |  | we will have to mark the property as sold. and will have to sync with CRM | send email recipt shouldn't be here. |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 8 | 7 | 8 | 7 | 21 | S
Home Page | Register for Auction | Display the list of shortlisted properties for auction |  |  | we will reuse the logic |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Home Page | Register for Auction | Register for Auction :: Add details + Upload documents + Set max bid limit | Upload License, Passport, Bank Statement ¦ Set Maximum Bid limit |  | this will have multiple screens, different for vendor and buyer, we will give document verification estimate separately, components will be reused from make an offer |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 21 | 16 | 13 | 11 | 21 | 16 | 43 | M
Home Page | Register for Auction | How Bid works? - Introduction video + Instructions | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 8 | 7 | 5 | 4 | 22 | S
Home Page | Register for Auction | Reverse Auction :: Set price alert (Notifications) |  |  | we will have to add priice alert mgmt, based on the design this might change, we will reuse the components from live auction |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 8 | 7 | 13 | 11 | 25 | S
Home Page | Register for Auction | Reverse Auction : Display current price, new price drop status bar | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 8 | 7 | 8 | 7 | 25 | S
Home Page | Register for Auction | Reverse Auction :: Buy now at current price | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Home Page | Register for Auction | Reverse Auction :: Bid successful |  |  | reuse the components from live auction |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Home Page | Register for Auction | Digital Signature |  |  | integration efforts will be separate, reuse the components |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Home Page | Register for Auction | Pay Deposit |  |  | reuse the components |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Home Page | Register for Auction | Payment Receipt (Download Invoice + Email Receipt) |  |  | reuse the components | email receipt shouldn't be present |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 2 | 1 | 7 | S
Home Page | Register for Auction | Live Auction Screen | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Home Page | Register for Auction | Live Auction :: Buyer can place multiple bids | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 34 | 24 | 13 | 11 | 8 | 7 | 42 | M
Home Page | Register for Auction | Once Bid approved by Vendor, proceed to sign + payment |  |  | reue the logic, these will be 2 screens as per the wireframe |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 8 | 7 | 5 | 4 | 18 | S
Home Page | Register for Auction | Live Auction :: Bid unsuccessful | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Home Page | Register for Auction | Reverse auction : Bid unsuccessful |  |  | we will reuse the component |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Home Page | Register for Auction | Make an offer:: Auction not started | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 8 | 7 | 2 | 1 | 15 | S
Home Page | My Properties | List of Properties |  |  | reuse the components from above |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Home Page | My Properties | View Status | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Home Page | My Properties | Withdraw bid | [7 empty] | Simple | Will not Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 |  | 0 |  | 0 |  | 0 | 0 | S
Home Page | My Properties | Request to forfeit the deal (Sale) | [7 empty] | Simple | Will not Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Home Page | My Properties | Download invoices |  |  | code will be reused | these are receipts, that the buyer has added |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 3 | 2 | 7 | S
Account | My Profile | Name | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 5 | 4 | 2 | 1 | 16 | S
Account | My Profile | Profile photo | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 2 | 1 | 5 | S
Account | My Profile | Verification badge | Profiles display indicators for verified email, phone, and other verifications (if any). Only fully verified users may be allowed to post listings or make transactions, to increase trust on the platform. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Account | My Profile | Reset Password |  |  | reuse the components from forgot password flow |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 2 | 1 | 7 | S
Account | My Shortlisted Properties | List |  |  | reuse the components |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Account | My Shortlisted Properties | View Details |  |  | reuse the components |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Account | My Shortlisted Properties | Remove from my list | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account | My Enquiries | List of Conversation Threads |  |  | we will have multiple screens here. |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 21 | 16 | 13 | 11 | 8 | 7 | 34 | M
Account | My Enquiries | Create a new Enquiry |  |  | this will be on the list view page, Assuming this will be a simple form | enquiry can be given against a listing only |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 3 | 2 | 5 | 4 | 13 | S
Account | My Enquiries | Conversation Interface |  |  |  | chat interface won't be there. |  |  |  | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 13 | 11 | 5 | 4 | 13 | 11 | 26 | S
Account | My Enquiries | Enquiry forms (Templates may differ 4-6) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 13 | 11 | 5 | 4 | 5 | 4 | 19 | S
Account | Manage Preferences | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 13 | 11 | 5 | 4 | 8 | 7 | 22 | S
Account :: Listings Management (Vendors only) | Listings List | List | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 5 | 4 | 7 | S
Account :: Listings Management (Vendors only) | Listings List | Search | [7 empty] | Simple | Could Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Account :: Listings Management (Vendors only) | Listings List | Sort | [7 empty] | Simple | Could Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Account :: Listings Management (Vendors only) | Listings List | Filter | [7 empty] | Simple | Could Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Account :: Listings Management (Vendors only) | View Listings | View Details |  |  | components will be reused |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 3 | 2 | 5 | S
Account :: Listings Management (Vendors only) | View Listings | Edit Details | [7 empty] | Simple | Will not Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Account :: Listings Management (Vendors only) | View Listings | Hide / Unhide | [7 empty] | Simple | Will not Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account :: Listings Management (Vendors only) | View Listings | Delete Listing | [7 empty] | Simple | Will not Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account :: Listings Management (Vendors only) | View Listings | Duplicate a Listing | [7 empty] | Simple | Will not Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 3 | 2 | 10 | S
Account :: Listings Management (Vendors only) | View Listings | Mark listing as Sold / Available / Not available |  |  | assuming this will be just a small cta or check , not a separate screen. |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Account :: Listings Management (Vendors only) | View Listings | Overall Market Insights of the properties | [7 empty] | Simple | Could Have |  |  |  |  | 3 | 2 | 3 | 2 |  | 0 |  | 0 |  | 0 | 0 | S
Account :: Listings Management (Vendors only) | Create New Listing | Select type of category ¦ Sale, Reverse Auction or Auction | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Account :: Listings Management (Vendors only) | Create New Listing | Add all the form details based on the type of form (3 types) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Create New Listing | Submit | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account :: Listings Management (Vendors only) | Create New Listing | Set Geo location and address | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Account :: Listings Management (Vendors only) | Create New Listing | Upload Images + Videos | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account :: Listings Management (Vendors only) | Create New Listing | Add FAQs | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Create New Listing | Add Terms and conditions | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 |  | 0 | 2 | 1 | 2 | S
Account :: Listings Management (Vendors only) | Create New Listing | Status :: Published or Sent for Admin Approval | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Accept Offer + Signature + Successful Screen | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Decline Offer + Comments | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Provide Counter offer | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 21 | 16 | 22 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View + Download signed agreement | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View. + Download Invoice (Multiple) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 3 | 2 | 3 | 2 | 5 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View the evidence documents submitted by Vendor | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View buyer profile | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 3 | 2 | 13 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Fill Property Evaluation Details + Photos | [7 empty] | Simple | Should Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 5 | 4 | 8 | 7 | 22 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Submission Successful | [7 empty] | Simple | Should Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 5 | 4 | 10 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | History of Property Evaluation Requests | [7 empty] | Simple | Should Have |  |  |  |  | 2 | 1 | 2 | 1 | 13 | 11 | 8 | 7 | 8 | 7 | 25 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Renovated - Admin has to provide a new estimation | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 5 | 4 | 3 | 2 | 10 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Not renovated - Immediate results via API | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Trigger a notification for new estimates | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 3 | 2 | 5 | 4 | 6 | S
Account :: Listings Management (Vendors only) | Add ons | View List of Attendees for Inspection | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Account :: Listings Management (Vendors only) | Add ons | Automated Buyer Feedback post Inspection | Post inspection, a feedback form should be triggered to the attendees about the property. |  | Assuming that we need to send a notification to buyer to get the feedback once the inspection is done., We are considering taking feedback in this sub-task only, | need to discuss this flow |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 13 | 11 | 22 | S
Account :: Listings Management (Vendors only) | Actions for Auction | Pause the auction | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 3 | 2 | 5 | 4 | 13 | S
Account :: Listings Management (Vendors only) | Actions for Auction | Update the Reserve price |  |  | assuming is at as "reverse" |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 3 | 2 | 11 | S
AI assistance | Chatbot |  |  |  | there will be only 1 chatbot, which can respond in multiple ways. Hence give estimates for only 1 chatbot., saving message history context for the chats will be AI sdk responsibility, hence not adding the estimates for that. |  |  |  |  | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 55 | 40 | 34 | 24 | 8 | 7 | 71 | M
In App Notifications + Deep Linking | Vendor Notifications | Offer accepted | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 8 | 7 | 13 | 11 | 13 | 11 | 29 | S
In App Notifications + Deep Linking | Vendor Notifications | Inspection requested | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
In App Notifications + Deep Linking | Vendor Notifications | New price update (valuation) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 1 | 0.5 | 2.5 | S
In App Notifications + Deep Linking | Buyer Notifications | Someone make an bid (auction) offer (private sale) | [7 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
In App Notifications + Deep Linking | Buyer Notifications | Property updated | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
In App Notifications + Deep Linking | Buyer Notifications | Someone made an enquiry | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
In App Notifications + Deep Linking | Buyer Notifications | Contact signed | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
In App Notifications + Deep Linking | Buyer Notifications | Auction about to start | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
In App Notifications + Deep Linking | Notification on every message |  |  |  |  | this might not be required |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Footer | T&Cs | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 8 | 7 | 0 | 0 | 18 | S
Footer | FAQs |  |  |  | reuse the components from above |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Footer | Legals |  |  |  | reuse the components from above | [5 empty] | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Footer | Help center |  |  |  | reuse the components from above |  |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Footer | Privacy Policy |  |  |  | reuse the components from above | [5 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Footer | Manage About Us |  |  |  | reuse the components from above | [5 empty] | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Logout | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 3 | S
Delete Account |  |  | Will manage via Contact us. | [6 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 |  | 0 |  | 0 |  | 0 | 0 | S
Push Notifications + Deep Linking |  |  |  |  | a lot of notification of different screens and flows have to be considered. |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 13 | 11 | 34 | 24 | 46 | M
Mobile Responsive + Mobile App |  |  |  |  | just a buffer to fix the edge cases |  |  |  |  | Simple | Must Have |  |  |  |  | 89 | 60 | 0 | 0 | 34 | 24 | 0 | 0 | 0 | 0 | 24 | S
UX Process | Requirement Gathering | [8 empty] | Simple | Must Have |  |  |  |  | 5 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Brainstorming & Research | [8 empty] | Simple | Must Have |  |  |  |  | 5 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | User Flow | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Competitive Analysis | [8 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Style Guide | [9 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Prototype | [9 empty] | Simple | Must Have |  |  |  |  | 13 | 11 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
RBAC |  |  |  |  | this might not be required with Auth0, this will be moved to admin portal |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 8 | 7 | 21 | 16 | 39 | M
Project setup | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 21 | 16 | 21 | 16 | 48 | M
Property Estimates |  |  |  |  | estimating according to the 1 screen in the wireframe. we will have to re estimate this once requirements are clear | Not sure what feature will be there, but I see a screen for this in framework. |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S
Campaign Selection | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 2 | 1 | 10 | S
Sync Enquiry From CRM |  |  |  |  | no FE efforts assumed here. |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | S
Additional Functionalities | Auction :: Set Reminder alert at a specific price | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Additional Functionalities | Private Sale :: Contract should support a dynamic date change (Hello Sign) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 3 | 2 | 8 | S
Additional Functionalities | Inspection | Public Inspection Request form (Buyer) --- Select number of attendees | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Additional Functionalities | Inspection | Private Inspection Request form (Buyer) ---- Date, Time and Attendees | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 3 | 2 | 3 | 2 | 5 | 4 | 8 | S
Additional Functionalities | Inspection | Inspection Scheduled (Buyer) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 2 | 1 | 2 | 1 | 6 | S
Additional Functionalities | Inspection | Inspection Requests (Seller) | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 2 | 1 | 2 | 1 | 6 | S
Additional Functionalities | Inspection | Register :: List of Attendees ( For Seller) - Mark attended/Not | [7 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 13 | 11 | 5 | 4 | 5 | 4 | 19 | S
Additional Functionalities | Inspection | Email triggers for inspection requests (To the seller and buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | S
Additional Functionalities | Inspection | Send Feedback Form via SMS (Buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | S
Additional Functionalities | Private Sale :: Special conditions in Listing Page | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Additional Functionalities | Private Sale :: Notify other buyers to place offers (When offer accepted by Seller) | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | S
Additional Functionalities | Live Auction :: Vendor must be able to place a bid | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 4 | S
Additional Functionalities | Contact Us (Email + Phone no) | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 3 | 2 | 2 | 1 | 10 | S
Additional Functionalities | Home :: My Enquiries (New Listings Requested + Property Evaluations) |  |  |  | ui can reused |  |  |  |  | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 | 2 | 1 | 7 | S
Additional Functionalities | Sale + Auction :: Request Legal Documents - Trigger email to Admin | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Additional Functionalities | Listings Page :: Show Valuations (Off Market) |  |  |  | this will come in My listings. but not sure how this will work with CRM | CRM sync needs to be figured out |  |  |  | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 8 | 7 | 15 | S
Email Templates (4-5) | [9 empty] | Simple | Must Have |  |  |  |  | 3 | 2 | 5 | 4 | 21 | 16 | 8 | 7 | 8 | 7 | 30 | S
Splash Screen | [9 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 |  | 0 |  | 0 |  | 0 | 0 | S
Crashlytics |  |  |  |  | we won't have have event based analytics. only product metric, which can be fetched from render analytics, hence no integration, no BE analytics, estimating only firebase crashlytics |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 8 | 7 | 3 | 2 | 9 | S
Digital Signature | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 34 | 24 | 34 | 24 | 55 | 40 | 88 | L
Stripe ID Verification | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 34 | 24 | 55 | 40 | 55 | 40 | 104 | L
CRM | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 8 | 7 | 89 | 60 | 67 | M
AI Functionalities | AI Enquiry Responder |  |  |  | UI efforts are given in vendor & buyer section |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 34 | 24 | 25 | S
AI Functionalities | Inspection Chatbot (Text + Voice) | Text | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 55 | 40 | 41 | M
AI Functionalities | Inspection Chatbot (Text + Voice) | Voice | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 89 | 60 | 61 | M
AI Functionalities | Document Parsing & RAG Setup |  | Uploaded documents will be parsed viva Python SDK layer and the text will be sent to OpenAI as a context. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 55 | 40 | 40 | M
AI Functionalities | AI QR Code Assistant |  |  |  | Reuse AI chatbot and this is just FE redirection |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Ably setup | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 8 | 7 | 21 | 16 | 23 | S
Bullmq | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Sendgrid :: Mails | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | S
Auth | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | S
Maps | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 34 | 24 | 13 | 11 | 21 | 16 | 51 | M
Message service (SMS) | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 7 | S
AVM integration |  |  |  |  | assuming some integration will be required for this on BE side. Haven't received much clarity from clients on this. |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 5 | 4 | 13 | 11 | 15 | S
Google Analytics | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 5 | 4 | 15 | S
Sentry | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 8 | 7 | 18 | S

## Mobile app - Vendor and - Dev
Module Name | Feature | Sub-Feature | Description | Reference Link | Assumption | Queries | Prototype Link | What to do? | How to do? | Complexity | Priority | Frequency | Design Available | Required Development | NPM Packages | Wireframes Story Points | 10.5 | Visual Design Story Points | 19.5 | Frontend Story Points | 413 | Integration Story Points | 291.5 | Backend Story Points | 9 | 713.5 | T-Shirt Size | Tags | Screen Patterns | Feature Categories
Website | Hero Section | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Website | About Unreserved | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Website | Types of Sale | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Website | Models | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Sign up | Social Login | Google | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Sign up | Social Login | Apple | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Sign up | Social Login | Facebook | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Sign up | Email and Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Sign up | Onboarding : Set Preferences | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Login | Email/Username + Password | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Login | Forgot Password | Provide email ID | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Login | Forgot Password | Send password reset email (15 min expiration) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Login | Forgot Password | Email clicks on password reset link | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Login | Forgot Password | New Password + Confirm Password | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Login | Forgot Password | Re-attempt login | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Login | Social Media Login :: Google, Apple, Facebook | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Home Page | Find a Property | Search a property | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Home Page | Find a Property | Filters : Type ¦ Budget ¦ Location ¦ Radius | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Home Page | Find a Property | List of Properties | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
Home Page | Find a Property | View property details | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Find a Property | Shortlist a property | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Home Page | Find a Property | View seller profile | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 0 | 0 | 3 | S
Home Page | Make an offer | Display the list of shortlisted properties for sale | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Make an offer | CTA :: Request for inspection |  |  | assuming this is where we take ke slot details. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | Make an offer | CTA :: Make an offer |  |  | Assuming this is where we give numbers / offers. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Home Page | Make an offer | Submit offer: Details to be added by Buyer and then Submit | Offer price, deposit amount, settlement terms, expiry date, special conditions and T&Cs. | [6 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home Page | Make an offer | Vendor accepts the offer or Proposes counter offer |  |  | Placement for this module will be in listing section and notifications. |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Home Page | Make an offer | Counter offer :: Accept or Decline | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Make an offer | Accepted :: Offer summary + Legal agreement with Sign | Third party integration for digital signature. |  | Stripe identity integration will be added separately |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 21 | 16 | 13 | 11 | 0 | 0 | 27 | S
Home Page | Make an offer | Proceed to Payment | Payment via Stripe |  | this will just show payment status on our end. and give upload receipt options. and at vendor's side it will show payment acknowledgement |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Make an offer | Payment confirmation : Download Invoice + Send Email Receipt |  |  | we will have to mark the property as sold. and will have to sync with CRM | send email recipt shouldn't be here. |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | Register for Auction | Display the list of shortlisted properties for auction |  |  | we will reuse the logic |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 5 | 4 | 0 | 0 | 6 | S
Home Page | Register for Auction | Register for Auction :: Add details + Upload documents + Set max bid limit | Upload License, Passport, Bank Statement ¦ Set Maximum Bid limit |  | this will have multiple screens, different for vendor and buyer, we will give document verification estimate separately |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 21 | 16 | 13 | 11 | 0 | 0 | 27 | S
Home Page | Register for Auction | How Bid works? - Introduction video + Instructions | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 7 | 8 | 7 | 0 | 0 | 14 | S
Home Page | Register for Auction | Reverse Auction : Display current price, new price drop status bar | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | Register for Auction | Reverse Auction :: Set price alert (Notifications) |  |  | we will have to add priice alert mgmt, based on the design, tis might change. |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Register for Auction | Reverse Auction :: Buy now at current price | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Home Page | Register for Auction | Reverse Auction :: Bid successful | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Register for Auction | Digital Signature |  |  | integration efforts will be separate |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Register for Auction | Pay Deposit | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Register for Auction | Payment Receipt (Download Invoice + Email Receipt) |  |  |  | email receipt shouldn't be present |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Home Page | Register for Auction | Live Auction Screen | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | Register for Auction | Live Auction :: Buyer can place multiple bids | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | Register for Auction | Once Bid approved by Vendor, proceed to sign + payment |  |  | reue the logic |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home Page | Register for Auction | Live Auction :: Bid unsuccessful | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 2 | 1 | 0 | 0 | 5 | S
Home Page | Register for Auction | Reverse auction : Bid unsuccessful | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home Page | My Properties | List of Properties |  |  | reuse the components from above |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Home Page | My Properties | View Status | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Home Page | My Properties | Download invoices |  |  | code will be reused | these are receipts, that the buyer has added |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Account | My Profile | Name | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account | My Profile | Profile photo | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Account | My Profile | Verification badge | Profiles display indicators for verified email, phone, and other verifications (if any). Only fully verified users may be allowed to post listings or make transactions, to increase trust on the platform. | [6 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Account | My Profile | Reset Password | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account | My Shortlisted Properties | List | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account | My Shortlisted Properties | View Details | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account | My Shortlisted Properties | Remove from my list | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
Account | My Enquiries | List of Conversation Threads |  |  | we will have multiple screens here. |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Account | My Enquiries | Create a new Enquiry |  |  |  | enquiry can be given against a listing only |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account | My Enquiries | Conversation Interface |  |  |  | chat interface won't be there. |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account | My Enquiries | Enquiry forms (Templates may differ 4-6) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 3 | 2 | 0 | 0 | 9 | S
Account | Manage Preferences | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 5 | 4 | 0 | 0 | 15 | S
Account :: Listings Management (Vendors only) | Listings List | List |  |  | main component will be reused |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Account :: Listings Management (Vendors only) | Listings List | Search | [7 empty] | Simple | Could Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 3 | 2 | 0 | 0 | 3 | S
Account :: Listings Management (Vendors only) | Listings List | Sort | [7 empty] | Simple | Could Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account :: Listings Management (Vendors only) | Listings List | Filter | [7 empty] | Simple | Could Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account :: Listings Management (Vendors only) | View Listings | View Details |  |  | components will be reused |  |  |  |  | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account :: Listings Management (Vendors only) | View Listings | Mark listing as Sold / Available / Not available | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Accept Offer + Signature + Successful Screen | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Decline Offer + Comments | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Account :: Listings Management (Vendors only) | Actions for Sale | Provide Counter offer | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View + Download signed agreement | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View. + Download Invoice (Multiple) | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 0 | 0 | 3 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View the evidence documents submitted by Vendor | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Account :: Listings Management (Vendors only) | Actions for Sale | View buyer profile | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Fill Property Evaluation Details + Photos | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Submission Successful | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | History of Property Evaluation Requests | [7 empty] | Simple | Should Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Renovated - Admin has to provide a new estimation | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Not renovated - Immediate results via API | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
Account :: Listings Management (Vendors only) | Property Valuation (Get Estimates) | Trigger a notification for new estimates | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | S
Account :: Listings Management (Vendors only) | Add ons | View List of Attendees for Inspection | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
Account :: Listings Management (Vendors only) | Add ons | Automated Buyer Feedback post Inspection | Post inspection, a feedback form should be triggered to the attendees about the property. |  |  | need to discuss this flow |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 3 | 2 | 8 | S
AI assistance | Chatbot |  |  |  | main component will be reused |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 13 | 11 | 8 | 7 | 0 | 0 | 18 | S
AI assistance | Enquiry Responder | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
AI assistance | Price Estimation | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
AI assistance | Inspection Chatbot (Text + Voice Input) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
AI assistance | QR Code / Property Link | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
List of forms | Contact Us form | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 8 | 7 | 5 | 4 | 0 | 0 | 11 | S
List of forms | Submit a Listing form (New) |  |  |  | this will sync with CRM webhook |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
In App Notifications + Deep Linking | Buyer Notifications | Someone make an bid (auction) offer (private sale) | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
In App Notifications + Deep Linking | Buyer Notifications | Property updated | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
In App Notifications + Deep Linking | Buyer Notifications | Someone made an enquiry | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
In App Notifications + Deep Linking | Buyer Notifications | Contact signed | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
In App Notifications + Deep Linking | Buyer Notifications | Auction about to start | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
In App Notifications + Deep Linking | Vendor Notifications | Inspection requested | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 2 | 1 | 0 | 0 | 5 | S
In App Notifications + Deep Linking | Vendor Notifications | Offer accepted | [7 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
In App Notifications + Deep Linking | Vendor Notifications | New price update (valuation) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
In App Notifications + Deep Linking | Notification on every message |  |  |  |  | this might not be required |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 5 | 4 | 5 | 4 | 12 | S
Footer | T&Cs | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 13 | 11 | 8 | 7 | 0 | 0 | 18 | S
Footer | FAQs | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Footer | Legals | [9 empty] | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Footer | Help center | [8 empty] | Simple | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Footer | Privacy Policy | [9 empty] | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Footer | Manage About Us | [9 empty] | Must Have |  |  |  |  | 1 | 0.5 | 1 | 0.5 | 5 | 4 | 5 | 4 | 0 | 0 | 8 | S
Logout | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | S
Push Notifications + Deep Linking |  |  |  |  | a lot of notification of different screens and flows have to be considered., most of the logic will be reused |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 13 | 11 | 0 | 0 | 27 | S
Mobile Responsive |  |  |  |  | just a buffer to fix the edge cases |  |  |  |  | Simple | Must Have |  |  |  |  | 8 | 7 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Requirement Gathering | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Brainstorming & Research | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | User Flow | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
UX Process | Competitive Analysis | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Style Guide | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Prototype | [9 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
RBAC |  |  |  |  | this might not be required with Auth0 |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project setup | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 21 | 16 | 21 | 16 | 0 | 0 | 32 | M
Property Estimates |  |  |  |  | maain component will be reused |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Campaign Selection |  |  |  |  | main component will be reused |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Sync Enquiry From CRM | [9 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | S
Additional Functionalities | Auction :: Set Reminder alert at a specific price | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Additional Functionalities | Private Sale :: Contract should support a dynamic date change (Hello Sign) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 5 | 4 | 0 | 0 | 6 | S
Additional Functionalities | Inspection | Public Inspection Request form (Buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Additional Functionalities | Inspection | Private Inspection Request form (Buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 3 | 2 | 0 | 0 | 4 | S
Additional Functionalities | Inspection | Email triggers for inspection requests | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Additional Functionalities | Inspection | Inspection Scheduled (Buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Additional Functionalities | Inspection | Inspection Requests (Seller) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Additional Functionalities | Inspection | Register :: List of Attendees ( For Seller) - Mark attended/Not | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 5 | 4 | 3 | 2 | 0 | 0 | 6 | S
Additional Functionalities | Inspection | Send Feedback Form via SMS (Buyer) | [7 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Additional Functionalities | Private Sale :: Special conditions in Listing Page | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Additional Functionalities | Private Sale :: Notify other buyers to place offers (When offer accepted by Seller) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Additional Functionalities | Live Auction :: Vendor must be able to place a bid | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | S
Additional Functionalities | Contact Us (Email + Phone no) | [8 empty] | Simple | Must Have |  |  |  |  | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Additional Functionalities | Home :: My enquires |  |  |  | ui can reused |  |  |  |  | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 1 | 0.5 | 0 | 0 | 2.5 | S
Additional Functionalities | Sale + Auction :: Request Legal Documents - Trigger email to Admin | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | S
Additional Functionalities | Listings Page :: Show Valuations (Off Market) | [8 empty] | Simple | Must Have | [5 empty] | 0 |  | 0 | 3 | 2 | 2 | 1 | 2 | 1 | 4 | S
Splash Screen | [9 empty] | Simple | Must Have |  |  |  |  | 2 | 1 | 2 | 1 | 5 | 4 | 3 | 2 |  | 0 | 6 | S

## Points-Table
M O S C O W | Range | Efforts | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
Story Points Matrix
Number | Hours | Efforts ( Time in Hours) | Difference in Time Duration | Different in Fib Points | % change in Time | % change in Fib Points
1 | <= 0.5 | 0.5 | 0.5 | 1 | 100 | 100
2 | 0.5 - 1 | 1 | 0.5 | 1 | 50 | 50
3 | 1 - 2 | 2 | 1 | 1 | 50 | 33.34
5 | 2 - 4 | 4 | 2 | 2 | 50 | 40
8 | 4 - 7 | 7 | 3 | 3 | 42.86 | 37.5
13 | 7 - 11 | 11 | 4 | 5 | 36.37 | 38.47
21 | 12 - 16 | 16 | 5 | 8 | 31.25 | 38.1
34 | 18 - 24 | 24 | 8 | 13 | 33.34 | 38.24
55 | 25 - 40 | 40 | 16 | 21 | 40 | 38.19
89 | 41 - 60 | 60 | 20 | 34 | 33.34 | 38.21
T- Shirt Sizing Matrix
Size | Range | Efforts
S | 0-32 | 32
M | 32-72 | 72
L | >=72 | 73
M O S C O W Matrix
M O S C O W
Must Have
Should Have
Could Have
Will not Have